## GANTT
Month | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48
WP1 Project Coordination & Management
T1.1 Scientific & Technical management
T1.2 Administrative and Operative management
T1.3 Quality and Risk management
T1.4 Data management
Deliverables |  |  | D1.1 |  |  | D1.2 | [5 empty] | D1.3 | [11 empty] | D1.3 | [11 empty] | D1.3 | [11 empty] | D1.4
WP2 Ethics
T2.1 Participant protection & ethical governance
T2.2 Data protection & regulatory compliance
T2.3 Equity, gender & ethical quality of interventions
Deliverables | D2.3/4/5 |  | D2.1/2/6
WP3 NCD Evidence Framework & Disease Context: behavioural underpinnings of interventions
T3.1 Obesity and metabolic health
T3.2 Mental health
T3.3 Addictions
T3.4 Mapping of behavioural determinants across disease areas
Deliverables
WP4 Multi-component Intervention 2, Co-creation and Planning: Upper secondary school/ late adolescence (age 16–18)
T4.1 Identification and selection of evidence-based intervention elements
T4.2 Co-creation and involvement process at intervention sites
T4.3 Developing intervention packages and implementation plans
Deliverables |  |  |  |  | D4.1
WP5 Multi-component Intervention 2, Co-creation and Planning: Adolescence / adult (age 18–25)
T5.1 Identification and selection of evidence-based intervention elements
T5.2 Co-creation and involvement process at intervention sites
T5.3 Developing intervention packages and implementation plans
Deliverables
WP6 Intervention Implementation in Countries
T6.1 Contextual analysis and implementation capacities
T6.2 Stakeholder mapping
T6.3 Core implementation science activities
T6.4 Case studies
T6.5 Synthesis and recommendations
Deliverables
WP7 Evaluation
T7.1 Real world data infrastructure
T7.2 Evaluation design
T7.3 Country-Level Impact assessment
T7.4 Synthesis, evidence packaging and recommendations
Deliverables | [47 empty] | D1.4
WP8 Sustainable implementation, Policy Simulation & Foresight
T8.1 Horizon scanning, prioritisation of drivers and participatorysense-making
T8.2 Policy simulation and modelling of long-term impacts
T8.3 Scenario development and stress testing of interventions
T8.4 Evaluation of integrated pathways, policyrecommendations and foresight uptake
Deliverables | [47 empty] | D1.4
WP9 Communication, Stakeholder engagement, Dissemination & Exploitation
T9.1 Dissemination, exploitation and communication plan
T9.2 Communication and project visibility
T9.3 Stakeholder engagement and targeted dissemination
T9.4 Exploitation, uptake and sustainability of project results
Deliverables | [47 empty] | D1.4
Year 1
Year 2
Year 4
Year 3