Z-HEALTH

REQUEST FOR CONTRIBUTIONS TO THE WP LEADER

| WP | Title | Leader |
| --- | --- | --- |
| WP1 | Project Coordination & Management | ICL |
| WP2 | Ethics | ICL/Ethics officer |
| WP3 | NCD Evidence Framework & Disease Context | ? |
| WP4 | Multi-component Intervention 2, Co-creation and Planning: Upper secondary school/ late adolescence (age 16–18) | NIPH |
| WP5 | Multi-component Intervention 2, Co-creation and Planning: Adolescence / adult (age 18–25) | ? |
| WP6 | Intervention implementation in Countries | NIJZ |
| WP7 | Evaluation | ICL |
| WP8 | Sustainable implementation, Policy Simulation & Foresight | ISINNOVA |
| WP9 | Communication, Stakeholder engagement, Dissemination & Exploitation | EuroHealthNet |

| Work package number | 4 | WP leader | NIPH |
| --- | --- | --- | --- |
| Work package title | Multi-component intervention 1, Co-creation and planning: lower secondary school/early adolescence (age 12-18) |  |  |
| Objectives O4.1 Identify, select and adapt multi-component interventions targeting obesity, mental health diseases and addictions O4.2 Explore to what extent meaningful youth involvement and co-creative processes with educators, health professionals and parents influence the successful or unsuccessful implementation of such interventions |  |  |  |
| Description of work T4.1 Identification and selection of evidence-based intervention (lead partner – role of participants). This task will undertake a systematic review of evidence-based interventions targeting the three selected disease conditions, drawing on both scientific and grey literature. Only interventions that have progressed to a minimum of Technology Readiness Level (TRL) ≥5—i.e., those that have been implemented and for which outcome data have been reported—will be included. The review will encompass interventions across the following four domains: (i) health and digital literacy; (ii) self-management of digital media use; (iii) healthy school environment and behavioural “nudge” interventions; and (iv) resource- and service-oriented interventions. Eligible studies will be identified through a comprehensive and reproducible search strategy, followed by systematic screening and data extraction procedures in accordance with established methodological standards. Each identified intervention will be critically appraised with respect to its effectiveness, the certainty and quality of the underlying scientific evidence, and its relevance across the different levels of the G1–G4 framework. This multi-level assessment will enable the identification of interventions that are not only effective but also scalable and contextually adaptable. In addition, particular emphasis will be placed on evaluating the extent to which the interventions explicitly address social inequalities in health. This will include assessing whether interventions are designed to reach disadvantaged populations, reduce barriers to access, or mitigate differential impacts across socioeconomic groups. The findings of this review will inform the subsequent selection and adaptation of interventions within the Z-HEALTH project, ensuring that they are both evidence-informed and equity-oriented. T4.2 Co-creation and involvement process at intervention sites (NIPH, PRESS lead partner – role of participants). Across all intervention packages and participating country sites, adolescents from the target population will be actively involved to ensure that their perspectives on both content and delivery formats are systematically incorporated. In each of the three participating countries, Group Model Building (GMB) sessions will be conducted with a minimum of three stakeholder groups, comprising adolescents, educators, parents, and health professionals. Participants will be recruited through youth organisations and established youth networks, with the explicit aim of achieving gender balance and representation across diverse socio-demographic backgrounds. The GMB process will facilitate the co-creation of shared conceptual models capturing the key drivers of risk behaviours related to non-communicable diseases (NCDs) within each local context. The insights generated will directly inform the adaptation, prioritisation, and implementation focus of the intervention packages, thereby enhancing their contextual relevance, acceptability, and potential effectiveness. Given the limited empirical evidence on adolescents’ perspectives regarding their involvement in intervention development, this project will place particular emphasis on documenting and analysing these experiences. A dedicated report will be produced to systematically capture youths’ reflections on their participation in the co-creation process which is lacking in the literature, including perceived benefits, challenges, and recommendations for future practice. This component will contribute to advancing methodological knowledge on meaningful youth engagement in health promotion research and intervention design. T4.3 Developing intervention packages and implementation plans The interventions to be included in the intervention packages will address key risk factors associated with obesity, mental health disorders, and addictions among adolescents. Each intervention will be systematically described with reference to its theoretical foundations, including the explicit definition and operationalisation of core concepts (e.g., health literacy). Furthermore, the underlying logical assumptions of each intervention will be critically assessed to determine the extent to which they align with established principles of evidence-informed health intervention design. To ensure a comprehensive understanding of the broader context in which these interventions operate, a systems perspective will be applied in the assessment. This will involve analysing the mechanisms, patterns, and dynamic interactions that contribute to the targeted disease burden, with the aim of identifying potential leverage points for sustainable system-level change. Such an approach will facilitate the integration of both individual- and structural-level determinants of health. The interventions will be iteratively adapted to the specific contexts of the participating sites, informed by insights generated through Group Model Building (GMB) sessions and ongoing engagement with adolescents. This co-creative process will ensure that the interventions are contextually relevant, culturally appropriate, and responsive to the needs and preferences of the target population. Finally, a dedicated implementation plan will be developed for each intervention. These plans will outline key components, delivery strategies, stakeholder roles, and evaluation considerations, thereby supporting the feasibility, scalability, and sustainability of the intervention packages across diverse settings. The preliminary focus of the intervention in the four policy domains are (i) health and digital literacy: school-based provision of health literacy lessons, digital literacy lessons and on management exposure of misinformation; (ii) self-management of digital media use: intervention for adolescents (and their families) on content access management tools, sleep duration and attention controls and notification frequency reduction tools; (iii) healthy school environment and behavioural “nudge” interventions: schools as health promoting environment, school food environment, physical activity interventions and smartphone-free schools; and (iv) resource- and service-oriented interventions: empowering adolescents to request and obtain safe advice and counselling from trained staff on health issues they may be experiencing or may be concerned about. |  |  |  |
| Deliverables D4.1 Systematic review D4.2 Report on youth involvement in intervention development D4.3 Health and digital literacy intervention description D4.4 Self-management of digital media use intervention description D4.5 Healthy school environments and nudges intervention description D4.6 Resource- and service-oriented intervention description Milestones M4.1 Intervention packages and implementation plans finalized Critical risks Individual-oriented interventions are typically designed on the implicit premise that individuals possess a sufficient degree of agency to modify their behaviours in response to health-promoting initiatives. However, this assumption may not hold uniformly across populations. Such interventions risk disproportionately benefiting individuals who already possess the requisite social, economic, and environmental resources to enact healthier choices, as well as those residing in contexts where such choices are more readily accessible. Consequently, a critical concern is that individual-oriented approaches may inadvertently exacerbate existing social inequalities in health by systematically privileging more advantaged groups. |  |  |  |

  - 1.1. Objectives and Ambition

1.1.2 State of the art and Ambition

Adolescence represents a critical developmental period marked by substantial physiological, cognitive, emotional, and social transitions. For individuals aged 12–18 years, this stage is further characterized by key educational transitions, including movement from primary to secondary and subsequently to upper secondary education. These transitions are accompanied by increasing autonomy from guardians and expanding social contexts. While such changes provide important opportunities for personal development and identity formation, they also constitute a vulnerable phase in which health-risk behaviours may emerge. The development of behaviours associated with non-communicable diseases (NCDs) among adolescents is shaped by a complex interplay of individual, social, and environmental determinants. Schools provide a key setting for health promotion, offering a structured and potentially equitable platform to enhance health literacy. However, the conceptualisation and measurement of adolescent health literacy remain inconsistent, limiting both the comparability of findings and the evaluation of interventions. In addition, the rapid expansion of digital media has amplified exposure to health-related misinformation, posing a significant challenge to effective health promotion and the development of critical health literacy skills. Addressing this issue requires innovative, context-sensitive approaches. Meaningful adolescent involvement in intervention design and implementation has been proposed as a promising strategy to improve relevance and engagement although empirical evidence remains limited. The Z-HEALTH project aims to strengthen adolescent health literacy by addressing misinformation and implementing intervention studies grounded in participatory, co-creative collaboration with adolescents, educators, health professionals, and parents.

  - Methodology

1.2.1 Overall methodology

Health promotion initiatives targeting children and adolescents have been extensively studied over recent decades. However, the rapidly evolving digital environment has introduced a proliferation of alternative information sources, many of which may adversely influence adolescents’ health behaviours and perceptions. In response, Z-HEALTH will implement a set of integrated interventions across four key policy domains, with a strong emphasis on empowerment and self-management through class-based activities; changes in school environment; resources and services for individual use. The intervention approach will be consistent with WHO’s guidelines on Health Promoting Schools, and with EuroHealthNet’s Schools4Health programme. Inclusiveness and sustainability will be key pillars of the intervention approach. First, a health and digital literacy programme will be co-created with adolescents and relevant local stakeholders, including school health services and community nurses where appropriate. This process will begin with a comprehensive needs assessment, followed by the development of an intervention plan comprising tailored health literacy materials and interactive, class-based sessions. Dedicated components will address digital literacy, with a focus on critically accessing and evaluating health information in digital media environments. Second, self-management interventions targeting digital media use will be offered to adolescents and their families who voluntarily participate. These programmes will support participants in modifying social media settings to reduce exposure to attention-capturing and potentially addictive features. Components will include tools for content access management, sleep duration and attention regulation, and notification frequency reduction. Third, interventions will address healthy school environments through a combination of food provision strategies, nutrition standards, and behavioural “nudges” (e.g., portion size, food presentation, and positioning). Where feasible and sustainable, these initiatives may be integrated with physical activity interventions. In addition, the feasibility of smartphone-free school environments will be explored. Fourth, resource- and service-oriented environmental interventions will aim to empower adolescents to seek and obtain confidential advice and counselling from trained professionals, with particular emphasis on mental health. This may involve adapting the Slovenian NIJZ “To sem jaz” digital counselling model to other contexts. All interventions will be developed through co-creative group model building workshops, workshops involving adolescents, educators, parents, and health professionals at each site. These workshops will generate shared conceptual models of key drivers of NCD-related risk behaviours, informing context-specific intervention plans. Health equity considerations will be systematically assessed using a dedicated health equity audit tool.

1.2.2 Interaction with other projects

NIPH serves as the scientific coordinator of the JA PreventNCD, and leads a technical work package. This initiative represents the largest European effort addressing risk factors for non-communicable diseases (NCDs) and cancer, aligned with the European Commission Healthier Together-EU Non-Communicable Diseases Initiative. JA PreventNCD includes over 25 countries and more than 100 governmental public health agencies which is unique opportunity for dissemination the Z-HEALTH project findings. NIJZ leads the sustainability work package, while EuroHealthNet contributes to dissemination, particularly towards policy decision-making. The project also features a dedicated Youth Advisory Group, highlighting its commitment to participatory approaches. NIPH previously coordinated the CO-CREATE project, (Horizon H2020 GA-ID:77421) on youth-focused obesity prevention. The youth organization PRESS was a key partner. CO-CREATE developed innovative tools, including the Dialogue Forum Tool, to support structured youth involvement in policymaking. Both JA PreventNCD and CO-CREATE have involved close collaboration with the WHO Regional Office for Europe, strengthening the scientific and policy impact of the project outputs.

Flodgren, G., Helleve, A., Selstø, A., Fismen, A. S., Blanchard, L., Rutter, H., & Klepp, K. I. (2025). Youth involvement in policy processes in public health, education, and social work—A scoping review. Obesity Reviews, 26(4), e13874.

Bröder, J., Okan, O., Bauer, U. et al. Health literacy in childhood and youth: a systematic review of definitions and models. BMC Public Health 17, 361 (2017). https://doi.org/10.1186/s12889-017-4267-y

Mastorci, F.; Lazzeri, M.F.L.; Vassalle, C.; Pingitore, A. The Transition from Childhood to Adolescence: Between Health and Vulnerability. Children 2024, 11, 989. https://doi.org/10.3390/children11080989

Masini, A., Salussolia, A., Anastasia, A. et al. Evaluation of school-based interventions including homework to promote healthy lifestyles: a systematic review with meta-analysis. J Public Health (Berl.) 34, 23–39 (2026). https://doi.org/10.1007/s10389-024-02239-6

Khanal SP, Budhathoki CB, Okan O, van Teijlingen E, Sharma MK, Acharya J, et al. Systematic review of

health literacy and health promotion in school-aged adolescents. J Educ Community Health. 2023; 10(1):49-57. doi:10.34172/jech.2023.1982

Ma, I., Sultan, M., Kozyreva, A. et al. Understanding the impact of misinformation on adolescents. Nat Hum Behav 10, 18–28 (2026). https://doi.org/10.1038/s41562-025-02338-8

Flodgren G, Helleve A, Selstø A, et al. Youth involvement in policy processes in public health, education, and social work—A scoping review. Obesity Reviews. 2025;26(4):e13874. doi:10.1111/obr.13874

Making every school a health-promoting school: implementation guidance. Geneva: World Health Organization and the United Nations Educational, Scientific and Cultural Organization; 2021.

EuroHealthNet (2024) Report on Policy and practice to strengthen the Health Promoting School approach across the

EU 31 January 2024

Hovmand PS. (2014) Community Based System Dynamics. New York: Springer. 26. Baum F et al. (2006).

Participatory action research. J Epidemiol Community Health. ;60(10):854-857

Savona, N et al (2021). Identifying the views of adolescents in five European countries on the drivers of obesity using group model building. European Journal of Public Health

31(2):391-396

https://www.gov.uk/government/publications/health-equity-assessment-tool-heat

https://www.preventncd.eu/

Klepp K-I, Helleve A, Høstrup E, et al. Scaling up non-communicable disease prevention and health promotion across Europe: The Joint Action PreventNCD. Scandinavian Journal of Public Health. 2025;53(3_suppl):8-17. doi:10.1177/14034948251352040

Helleve A, Gregório MJ, Bergsvik D, et al. Strengthening the use of regulatory policy measures for prevention of NCDs in Europe through the JA PreventNCD project. Scandinavian Journal of Public Health. 2025;53(3_suppl):27-34. doi:10.1177/14034948251374402

https://cordis.europa.eu/project/id/774210

Klepp K-I, Helleve A, Brinsden H, et al. Overweight and obesity prevention for and with adolescents: The “Confronting obesity: Co-creating policy with youth” (CO-CREATE) project. Obesity Reviews. 2023;24(S1):e13540. doi:10.1111/obr.13540

Ulloa MA, Nesrallah S, Shafafi P, et al. Designing a youth-led Dialogue Forum tool: The CO-CREATE experience. Obesity Reviews. 2023;24(S2):e13611. doi:10.1111/obr.13611