Z-HEALTH proposal

Behavioural interventions as primary prevention for Non-Communicable Diseases (NCDs) among young people

deadline: 16 April 2026

Proposal preparation timeline

| Work package structure to partners and Request of intervention description | ICL to partners | 04/03/2026 |
| --- | --- | --- |
| Contribution from partners: ideas of intervention description and thoughts (including possible roles) | Partners to Management team | 09/03/2026 |
| Conference call to discuss and define proposal structure, interventions and roles/contributions | All partners | 10/03/2026 (from 2 to 5 p.m.) |
| Circulation of proposal template: assignment of sections to partners and WP leadership | Management team to partners | 11/03/2026 |
| Fine tuning of the intervention descriptions | Partners to Management team | 13/03/2026 |
| Definition of the WP tasks (including possible roles) | WP leaders to Management team | 13/03/2026 |
| Conference call to validate WP structure and tasks | All partners | 13/03/2026 (from 3 to 5 p.m.) |
| Contribution to section 1-2 and WP descriptions | All partners to ISINNOVA | 19/03/2026 |
| Elaboration of 2nd draft proposal | ISINNOVA to partners | 24/03/2026 |
| Conference call to discuss proposal contents | Partners | 30/03/2026 (from 2 to 5 p.m.) |
| Contributions from all partners to WP leaders | Partners to WP leaders | 02/04/2026 |
| Elaboration of 3rd draft proposal and first draft of budget | ISINNOVA to partners | 07/04/2026 |
| Submission of the Proposal | ISINNOVA | 16 April 2026 |