| Work package number | 4 | WP leader | NIPH |
| --- | --- | --- | --- |
| Work package title | Multi-component intervention 1, Co-creation and planning: lower secondary school/early adolescence (age 12-18) |  |  |
| Objectives O4.1: Identify, select and adapt multi-component interventions targeting obesity, mental health diseases and addictions O4.2: Explore to what extent meaningful youth involvement and co-creative processes with educators, health professionals and parents influence the successful or unsuccessful implementation of such interventions |  |  |  |
| Description of work T4.1 Identification and selection of evidence-based intervention elements (NIPH). Z-HEALTH will implement multi-component interventions targeting adolescents aged 12–18 across four policy domains: (i) health and digital literacy; (ii) self-management of digital media use; (iii) healthy school environments and behavioural “nudges”; and (iv) resource- and service-oriented interventions. A review of interventions addressing the three target disease areas will be conducted using scientific and grey literature. Interventions will be appraised for effectiveness, quality and certainty of evidence, and relevance across the G1–G4 framework, with particular attention to scalability, contextual adaptability, and their potential to reduce social inequalities. T4.2 Co-creation and involvement process at intervention sites (NIPH, PRESS). Adolescents will be actively involved across all intervention packages to ensure relevance of content and delivery. In each country, Group Model Building (GMB) sessions will be conducted with adolescents, educators, parents, and health professionals, recruited via youth networks to ensure diversity and gender balance. These sessions will generate shared models of NCD risk behaviours and inform intervention adaptation. Given limited evidence on youth involvement, adolescents’ experiences of participation will be systematically documented. T4.3 Developing intervention packages and implementation plans (NIPH, ICL, NYC, EHN, NIJZ). Interventions will be described in terms of theoretical foundations, core concepts, and underlying assumptions, and analysed using a systems perspective to identify mechanisms and leverage points for change. They will be iteratively adapted based on GMB outputs and youth engagement and adapted to the specific contexts of the participating sites to ensure that the interventions are contextually relevant, culturally appropriate, and responsive to the needs and preferences of the target population. A dedicated implementation plan based on specific needs assessment will be developed for each intervention (tasks 4.3.1-4.3.4 below). T4.3.1 The health and digital literacy intervention (ICL, NIPH) – A co-created health and digital literacy programme with youth and relevant local stakeholders. Involvement of school health services and community nurses (where relevant). Components may include the following: a) TUTCH (Teenagers understanding and taking control of their health) educational approach, developed by the CHOICE Foundation (SE) based on training medical students to deliver health literacy sessions to adolescents on mental health and addictions. b) Digital literacy sessions, focusing on access to health information through digital media. Understanding how AI algorithms affect the health-related information young people access. Managing exposure to misinformation through pre-bunking and inoculation. A component of the digital literacy programme will be designed to support domain no. 2 in the intervention package, described below. T4.3.2 Self-management of digital media use intervention (NYU) – An individual-level intervention component, requiring children (and their families) to volunteer to modify their social media settings in ways that will limit their exposure to “attention grabbing” and potentially addictive features of digital media use. These interventions will include the following: a) Content access management tool, hindering “infinite scrolling” which will prevent children from excessive exposure to social media content and from spending exceeding amounts of time on screens and digital media, thereby reducing exposure to potentially harmful health-related content. b) Sleep duration and attention controls, which would trigger a hard stop (not amenable to manipulation) on social media use at given times of the day and night. c) Notification frequency reduction tool, which would reduce the frequency of notifications, another key “attention grabbing” feature of digital media use, by delivering them in batches, thereby reducing the frequency of device pick-up and time spent on digital devices. T4.3.3 Healthy school environment and behavioural “nudge” interventions (EHN, ICL) - School-level intervention component aimed at creating a health promoting environment. The interventions will consist of a) Alignment with WHO policy guidelines and recommendations for school food environments related to direct food provision; nutrition standards; and nudges (portion size, nutrition information, food presentation and positioning). While not all schools would have canteens or directly provide full meals, there is probably sufficient scope for implementing food environment interventions that would have a meaningful impact on children’s dietary intakes. b) Food environment interventions that can be combined with physical activity interventions in addressing the first critical health area (overweight and obesity), provided that the required infrastructure investment is affordable and sustainable. c) Smartphone-free schools, following an increasing number of jurisdictions preventing children from taking their smartphones to school or using them while at school. T4.3.4 Resources and services intervention (NIJZ) - Environmental interventions aimed at empowering children to request and obtain safe advice and counselling from trained staff on health issues they may be experiencing or may be concerned about. The priority area in this domain will be mental health, and the intervention may rely on transferring and adapting the NIJZ approach developed in Slovenia with the “To sem jaz” mental health counselling website or similar resources in the other countries. Potentially, an AI-assisted version of NIJZ’s tool could be considered, for efficiency of deliver, while maintaining trained staff in control of the answers provided. The AI support algorithm could be trained using a database of questions asked and advice provided over the years (if available) in Slovenia. |  |  |  |
| Deliverables D4.1 Systematic review M6 D4.2 Report on youth involvement in intervention development M12 D4.3 Health and digital literacy intervention description M9 D4.4 Self-management of digital media use intervention description M9 D4.5 Healthy school environments and nudges intervention description M9 D4.6 Resource- and service-oriented intervention description M9 Milestones M4.1 Intervention packages and implementation plans finalized Critical risks Individual-oriented interventions are typically designed on the implicit premise that individuals possess a sufficient degree of agency to modify their behaviours in response to health-promoting initiatives. However, this assumption may not hold uniformly across populations. Such interventions risk disproportionately benefiting individuals who already possess the requisite social, economic, and environmental resources to enact healthier choices, as well as those residing in contexts where such choices are more readily accessible. Consequently, a critical concern is that individual-oriented approaches may inadvertently exacerbate existing social inequalities in health by systematically privileging more advantaged groups. |  |  |  |

  - 1.1. Objectives and Ambition

1.1.2 State of the art and Ambition

Adolescence represents a critical developmental period marked by substantial physiological, cognitive, emotional, and social transitions. For individuals aged 12–18 years, this stage is further characterized by key educational transitions, including movement from primary to secondary and subsequently to upper secondary education. These transitions are accompanied by increasing autonomy from guardians and expanding social contexts. While such changes provide important opportunities for personal development and identity formation, they also constitute a vulnerable phase in which health-risk behaviours may emerge. The development of behaviours associated with non-communicable diseases (NCDs) among adolescents is shaped by a complex interplay of individual, social, and environmental determinants. Schools provide a key setting for health promotion, offering a structured and potentially equitable platform to enhance health literacy. However, the conceptualisation and measurement of adolescent health literacy remain inconsistent, limiting both the comparability of findings and the evaluation of interventions. In addition, the rapid expansion of digital media has amplified exposure to health-related misinformation, posing a significant challenge to effective health promotion and the development of critical health literacy skills. Addressing this issue requires innovative, context-sensitive approaches. Meaningful adolescent involvement in intervention design and implementation has been proposed as a promising strategy to improve relevance and engagement although empirical evidence remains limited. The Z-HEALTH project aims to strengthen adolescent health literacy by addressing misinformation and implementing intervention studies grounded in participatory, co-creative collaboration with adolescents, educators, health professionals, and parents.

  - Methodology

1.2.1 Overall methodology

Health promotion initiatives targeting children and adolescents have been extensively studied over recent decades. However, the rapidly evolving digital environment has introduced a proliferation of alternative information sources, many of which may adversely influence adolescents’ health behaviours and perceptions. In response, Z-HEALTH will implement a set of integrated interventions across four key policy domains, with a strong emphasis on empowerment and self-management through class-based activities; changes in school environment; resources and services for individual use. The intervention approach will be consistent with WHO’s guidelines on Health Promoting Schools, and with EuroHealthNet’s Schools4Health programme. Inclusiveness and sustainability will be key pillars of the intervention approach. First, a health and digital literacy programme will be co-created with adolescents and relevant local stakeholders, including school health services and community nurses where appropriate. This process will begin with a comprehensive needs assessment, followed by the development of an intervention plan comprising tailored health literacy materials and interactive, class-based sessions. Dedicated components will address digital literacy, with a focus on critically accessing and evaluating health information in digital media environments. Second, self-management interventions targeting digital media use will be offered to adolescents and their families who voluntarily participate. These programmes will support participants in modifying social media settings to reduce exposure to attention-capturing and potentially addictive features. Components will include tools for content access management, sleep duration and attention regulation, and notification frequency reduction. Third, interventions will address healthy school environments through a combination of food provision strategies, nutrition standards, and behavioural “nudges” (e.g., portion size, food presentation, and positioning). Where feasible and sustainable, these initiatives may be integrated with physical activity interventions. In addition, the feasibility of smartphone-free school environments will be explored. Fourth, resource- and service-oriented environmental interventions will aim to empower adolescents to seek and obtain confidential advice and counselling from trained professionals, with particular emphasis on mental health. This may involve adapting the Slovenian NIJZ “To sem jaz” digital counselling model to other contexts. All interventions will be developed through co-creative group model building workshops, workshops involving adolescents, educators, parents, and health professionals at each site. These workshops will generate shared conceptual models of key drivers of NCD-related risk behaviours, informing context-specific intervention plans. Health equity considerations will be systematically assessed using a dedicated health equity audit tool.

1.2.2 Interaction with other projects

NIPH serves as the scientific coordinator of the JA PreventNCD, and leads a technical work package. This initiative represents the largest European effort addressing risk factors for non-communicable diseases (NCDs) and cancer, aligned with the European Commission Healthier Together-EU Non-Communicable Diseases Initiative. JA PreventNCD includes over 25 countries and more than 100 governmental public health agencies which is unique opportunity for dissemination the Z-HEALTH project findings. NIJZ leads the sustainability work package, while EuroHealthNet contributes to dissemination, particularly towards policy decision-making. The project also features a dedicated Youth Advisory Group, highlighting its commitment to participatory approaches. NIPH previously coordinated the CO-CREATE project, (Horizon H2020 GA-ID:77421) on youth-focused obesity prevention. The youth organization PRESS was a key partner. CO-CREATE developed innovative tools, including the Dialogue Forum Tool, to support structured youth involvement in policymaking. Both JA PreventNCD and CO-CREATE have involved close collaboration with the WHO Regional Office for Europe, strengthening the scientific and policy impact of the project outputs.

Mastorci, F.; Lazzeri, M.F.L.; Vassalle, C.; Pingitore, A. The Transition from Childhood to Adolescence: Between Health and Vulnerability. Children 2024, 11, 989. https://doi.org/10.3390/children11080989

Masini, A., Salussolia, A., Anastasia, A. et al. Evaluation of school-based interventions including homework to promote healthy lifestyles: a systematic review with meta-analysis. J Public Health (Berl.) 34, 23–39 (2026). https://doi.org/10.1007/s10389-024-02239-6

Khanal SP, Budhathoki CB, Okan O, van Teijlingen E, Sharma MK, Acharya J, et al. Systematic review of

health literacy and health promotion in school-aged adolescents. J Educ Community Health. 2023; 10(1):49-57. doi:10.34172/jech.2023.1982

Ma, I., Sultan, M., Kozyreva, A. et al. Understanding the impact of misinformation on adolescents. Nat Hum Behav 10, 18–28 (2026). https://doi.org/10.1038/s41562-025-02338-8

Flodgren G, Helleve A, Selstø A, et al. Youth involvement in policy processes in public health, education, and social work—A scoping review. Obesity Reviews. 2025;26(4):e13874. doi:10.1111/obr.13874

Making every school a health-promoting school: implementation guidance. Geneva: World Health Organization and the United Nations Educational, Scientific and Cultural Organization; 2021.

EuroHealthNet (2024) Report on Policy and practice to strengthen the Health Promoting School approach across the

EU 31 January 2024

Hovmand PS. (2014) Community Based System Dynamics. New York: Springer. 26. Baum F et al. (2006).

Participatory action research. J Epidemiol Community Health. ;60(10):854-857

Savona, N et al (2021). Identifying the views of adolescents in five European countries on the drivers of obesity using group model building. European Journal of Public Health

31(2):391-396

https://www.gov.uk/government/publications/health-equity-assessment-tool-heat

https://www.preventncd.eu/

Klepp K-I, Helleve A, Høstrup E, et al. Scaling up non-communicable disease prevention and health promotion across Europe: The Joint Action PreventNCD. Scandinavian Journal of Public Health. 2025;53(3_suppl):8-17. doi:10.1177/14034948251352040

Helleve A, Gregório MJ, Bergsvik D, et al. Strengthening the use of regulatory policy measures for prevention of NCDs in Europe through the JA PreventNCD project. Scandinavian Journal of Public Health. 2025;53(3_suppl):27-34. doi:10.1177/14034948251374402

https://cordis.europa.eu/project/id/774210

Klepp K-I, Helleve A, Brinsden H, et al. Overweight and obesity prevention for and with adolescents: The “Confronting obesity: Co-creating policy with youth” (CO-CREATE) project. Obesity Reviews. 2023;24(S1):e13540. doi:10.1111/obr.13540

Ulloa MA, Nesrallah S, Shafafi P, et al. Designing a youth-led Dialogue Forum tool: The CO-CREATE experience. Obesity Reviews. 2023;24(S2):e13611. doi:10.1111/obr.13611