Page limit: The title, list of participants and sections 1, 2 and 3, together, should not be longer than XX pages. All tables, figures, references and any other element pertaining to these sections must be included as an integral part of these sections and are thus counted against this page limit. The number of pages included in each section of this template is only indicative.

Experts will be instructed to ignore hyperlinks to information that is specifically designed to expand the proposal, thus circumventing the page limit.

The reference font for the body text of proposals is Times New Roman (Windows platforms), Times/Times New Roman (Apple platforms) or Nimbus Roman No. 9 L (Linux distributions).

The use of a different font for the body text is not advised and is subject to the cumulative conditions that the font is legible and that its use does not significantly shorten the representation of the proposal in number of pages compared to using the reference font (for example with a view to bypass the page limit).

The minimum font size allowed is 11 points. Standard character spacing and a minimum of single line spacing is to be used. This applies to the body text, including text in tables.

Text elements other than the body text, such as headers, foot/end notes, captions, formula's, may deviate, but must be legible.The page size is A4, and all margins (top, bottom, left, right) should be at least 15 mm (not including any footers or headers).

| DEFINITIONS |  |
| --- | --- |
| Critical risk | A critical risk is a plausible event or issue that could have a high adverse impact on the ability of the project to achieve its objectives. Level of likelihood to occur (Low/medium/high): The likelihood is the estimated probability that the risk will materialise even after taking account of the mitigating measures put in place. Level of severity (Low/medium/high): The relative seriousness of the risk and the significance of its effect. |
| Impacts | Wider long term effects on society (including the environment), the economy and science, enabled by the outcomes of R&I investments (long term). It refers to the specific contribution of the project to the CBE JU expected impacts described in the Strategic Research and Innovation Agenda (SRIA) (https://www.cbe.europa.eu/system/files/2022-06/cbeju-sria.pdf). Impacts generally occur some time after the end of the project. |
| Pathway to impact | Logical steps towards the achievement of the expected impacts of the project over time, in particular beyond the duration of a project. A pathway begins with the projects’ results, to their dissemination, exploitation and communication, contributing to the expected outcomes described in the CBE JU annual work programme topic, and ultimately to the wider scientific, economic and societal impacts of the CBE JU and of its Strategic Research and Innovation Agenda (SRIA) (https://www.cbe.europa.eu/system/files/2022-06/cbeju-sria.pdf). |

Guidance on the use of generative AI tools for the preparation of the proposal

When considering the use of generative artificial intelligence (AI) tools for the preparation of the proposal, it is imperative to exercise caution and careful consideration. The AI-generated content should be thoroughly reviewed and validated by the applicants to ensure its appropriateness and accuracy, as well as its compliance with intellectual property regulations. Applicants are fully responsible for the content of the proposal (even those parts produced by the AI tool) and must be transparent in disclosing which AI tools were used and how they were utilized. Specifically, applicants are required to: - Verify the accuracy, validity, and appropriateness of the content and any citations generated by the AI tool and correct any errors or inconsistencies. - Provide a list of sources used to generate content and citations, including those generated by the AI tool. Double-check citations to ensure they are accurate and properly referenced. - Be conscious of the potential for plagiarism where the AI tool may have reproduced substantial text from other sources. Check the original sources to be sure you are not plagiarizing someone else’s work. - Acknowledge the limitations of the AI tool in the proposal preparation, including the potential for bias, errors, and gaps in knowledge.

Part B: technical description

Z-HEALTH - Title of the ProposaL

List of participants

| ##### Participant No. * | ##### Participant organisation name | ##### Short name | ##### Country |
| --- | --- | --- | --- |
| ##### 1 (Coordinator) | Imperial College of Science Technology & Medicine | ICL | UK |
| ##### 2 | ISINNOVA | ISS | IT |
| ##### 3 | Norwegian Institute of Public Health | NIPH | NO |
| ##### 4 | Slovenian National Institute of Public Health | NIJZ | SI |
| ##### 5 | EuroHealthNet ASBL | EHNet | BE |
| ##### 6 | New York University | NYU | USA |
| ##### 7 | University of Copenhagen | UCPH | CPH |
| ##### 8 | University of Cologne | UoC | DE |

- Excellence

Excellence – aspects to be taken into account. - Clarity and pertinence of the project’s objectives, and the extent to which the proposed work is ambitious, and goes beyond the state of the art. - Soundness of the proposed methodology, including the underlying concepts, models, assumptions, interdisciplinary approaches, appropriate consideration of the gender dimension in research and innovation content, and the quality of open science practices, including sharing and management of research outputs and engagement of citizens, civil society and end users where appropriate.

- The following aspects will be taken into account only to the extent that the proposed work is within the scope of the work programme topic.

  - Objectives and ambition

4 PAGES

- Briefly describe the objectives of your proposed work. Why are they pertinent to the work programme topic? Are they measurable and verifiable? Are they realistically achievable?

- Describe how your project goes beyond the state-of-the-art, and the extent the proposed work is ambitious. Indicate any exceptional ground-breaking R&I, novel concepts and approaches, new products, services or business and organisational models. Where relevant, illustrate the advance by referring to products and services already available on the market. Refer to any patent or publication search carried out.

- Describe where the proposed work is positioned in terms of R&I maturity (i.e. where it is situated in the spectrum from ‘idea to application’, or from ‘lab to market’). Where applicable, provide an indication of the Technology Readiness Level, if possible distinguishing the start and by the end of the project.

- Please bear in mind that advances beyond the state of the art must be interpreted in the light of the positioning of the project. Expectations will not be the same for RIAs at lower TRL, compared with Innovation Actions at high TRLs.

| Contribution from WP8 | Strategic foresight is increasingly embedded in EU policymaking, notably through the European Commission’s Strategic Foresight Reports and the JRC Foresight Framework, supporting anticipatory governance and policy design. International organisations (e.g. OECD, World Economic Forum) have further expanded foresight approaches to address technological, societal, and behavioural transformations. While foresight for policy design is well established, its application in public health—particularly for NCD prevention—remains limited. Existing initiatives rarely combine participatory approaches, behavioural science and intervention research in a single analytical framework and only occasionally integrate youth perspectives and diverse socio-economic contexts in a systematic way. Z-HEALTH addresses this gap by embedding participatory foresight within its research, implementation and policy transition framework.. WP8 combines horizon scanning, social media analysis, youth participation, collective sense-making, andDelphi processes to identify emerging trends and uncertainties shaping youth health behaviours across diverse socio-economic contexts. The project advances the state of the art by linking foresight outputs with intervention evaluation and modelling. Scenario-based analysis will assess the robustness, scalability, and equity implications of behavioural interventions under alternative future conditions, supporting adaptive, evidence-based, and policy-relevant strategies for NCD prevention. This allows Z-HEALTH not only to evaluate what works today, but also to anticipate what may remain effective, acceptable, and fair in the youth health environments of the future. |
| --- | --- |

The burden: three diseases, one generation, one intervention window

Non-communicable diseases (NCDs) are the leading cause of death and disability in Europe, accounting for approximately 90% of all mortality. Among adults, NCD burden accumulates over decades — but the biological, behavioural, and social conditions that determine lifetime NCD risk are set during adolescence and early adulthood, between the ages of 12 and 25. Sawyer et al. established this window as the single most consequential period for long-term health trajectories.1 It follows, therefore, that NCD prevention investments directed at this age group carry the highest potential return — and the longest window before harm is irreversible.

Europe is currently failing this generation across three interconnected disease domains. Z-HEALTH targets each one directly, starting from the disease — its burden, its biology, and its modifiable causes — and working backwards to the interventions that can change its course.

### Obesity

Obesity (ICD-11 5B81) is a chronic, progressive, relapsing disease — not a risk factor, a lifestyle failing, or a side-effect of other conditions. The WHO recognises obesity as a disease in its own right, with distinct pathophysiology, defined diagnostic criteria, and independent attributable mortality. In European youth, the scale is now alarming: across 35 countries participating in the WHO COSI study, 29% of children and adolescents are overweight or obese,2 with the highest rates in Southern and Eastern Europe exceeding 40%. Garrido-Miguel et al. (2019), in a systematic review and meta-analysis of 103 studies covering 636,933 European children aged 3–16, documented a monotonic increase in obesity prevalence from 1999 to 2016 in virtually every country studied.3

The consequences of adolescent obesity are severe and compound. Obesity in adolescence is associated with a 5-fold increase in the risk of adult obesity,2 and directly predicts incident type 2 diabetes, cardiovascular disease, non-alcoholic fatty liver disease, hypertension, obstructive sleep apnoea, and several cancers in adulthood. Beyond physical comorbidity, adolescent obesity is strongly associated with depression, anxiety, and eating disorders — a bidirectional relationship that amplifies both conditions. The economic cost of obesity in the EU is estimated at over €70 billion annually in direct healthcare expenditure and productivity losses.

The primary behavioural driver in young people is dietary quality, specifically consumption of ultra-processed foods (UPFs) — industrially manufactured products containing additives, emulsifiers, and engineered palatability profiles that override normal satiety signalling. UPF now comprises over 50% of dietary energy intake among adolescents in the UK, and between 30–48% in France, Germany, and the Nordic countries.4 Physical inactivity compounds this: fewer than 20% of European adolescents meet WHO guidelines for moderate-to-vigorous physical activity.

### Mental health diseases

Mental disorders among young Europeans are not a homogeneous category — they are a family of distinct diseases with different aetiologies, different intervention targets, and different trajectories. Z-HEALTH focuses on three that dominate the burden in the 12–25 age group and share common digital environment exposure pathways.

Depression and anxiety (ICD-11 6A70–6B04) are the leading causes of disability-adjusted life years (DALYs) in European youth. Castelpietra et al. (2022), analysing Global Burden of Disease data for 30 European countries from 1990 to 2019, found that mental disorders, substance use disorders, and self-harm collectively accounted for approximately 15% of all DALYs in the 10–24 age group.5 The Lancet Psychiatry Commission on youth mental health (McGorry et al., 2024) identified a global youth mental health crisis, with 75% of adult mental disorders having their onset before age 25 and prevalence of anxiety and depression in European youth rising sharply from 2012 onwards — a rise that correlates temporally with the proliferation of smartphone social media.6

Sleep disorders (ICD-11 7A00–7A20) are insufficiently recognised as diseases in their own right, yet they carry substantial independent morbidity. Chronic sleep insufficiency in adolescence is associated with increased risk of depression, anxiety, obesity, type 2 diabetes, and cardiovascular disease. Carter et al. (2016) demonstrated in a systematic review and meta-analysis that portable screen-based media access was significantly associated with reduced sleep duration (OR 2.17) and poor sleep quality (OR 1.46).7 European data show that 30–40% of adolescents report insufficient sleep, a proportion that has increased in parallel with smartphone adoption.

Eating disorders (ICD-11 6B80–6B84) — including anorexia nervosa, bulimia nervosa, and binge-eating disorder — have the highest mortality of any mental health condition, with standardised mortality ratios up to 6 times that of the general population. They disproportionately onset in the 12–20 age range, are exacerbated by social media-mediated body image exposure, and are increasingly comorbid with obesity as binge-eating disorder becomes the most prevalent eating disorder subtype.

### Addictions

Addictions are diseases. Alcohol use disorder (ICD-11 6C40), nicotine/vaping dependence (6C4A), gambling disorder (6C50), and gaming disorder (6C51) are classified under ICD-11 Chapter 6C (Disorders due to substance use or addictive behaviours). They share a neurobiological substrate — dysregulation of dopaminergic reward circuitry — and a developmental vulnerability: the adolescent brain is disproportionately susceptible to addiction onset because prefrontal inhibitory control is not fully mature until age 25.

The scale of the problem in European youth is substantial. Hazardous alcohol use affects approximately 12–15% of young people aged 15–24, with binge drinking patterns established in adolescence predicting lifetime alcohol use disorder.5 Vaping (nicotine/electronic cigarette use) has escalated sharply: the WHO European Regional Office reported in 2025 that the EU has the highest rate of youth e-cigarette use globally, with 32% of 13–15 year-olds in some countries having tried e-cigarettes.8 Tarasenko et al. (2022), analysing Global Youth Tobacco Survey data across 17 European sites, found current e-cigarette use of 5–22% among adolescents depending on country.9

Problem gambling is emerging as a significant youth disorder: Calado et al. (2017), in a systematic review of 44 studies, found problem gambling prevalence of 0.2–12.3% among adolescents, with higher rates among males and digital/online gamblers.10 All three addiction domains share a critical characteristic: digital environments are the primary contemporary vector for onset and escalation — through advertising, platform design, and the social normativisation of addictive products and behaviours in algorithmically curated feeds.

### Why 12–25 is the intervention window that matters

All three conditions share a developmental compression point. Sawyer et al. established that 70% of adult mental health disorders have their first onset before age 25;1 obesity tracks from childhood to adulthood with high persistence;2 and addiction disorders onset overwhelmingly in the 15–24 window, with earlier onset predicting greater severity.10 The biological basis for this compression is neurodevelopmental: adolescence is characterised by heightened neuroplasticity — greater capacity for habit formation and, critically, greater responsiveness to intervention — combined with incompletely developed prefrontal inhibitory control. This creates a window in which environmental influences shape disease trajectories that persist for life, and in which well-timed behavioural interventions can change those trajectories in ways that become progressively harder to achieve with age.

Europe's 90 million young people aged 12–25 are moving through this window right now. The generation currently in it is the first to have spent their formative years immersed in pervasive, algorithmically curated digital environments — and the NCD epidemiology of this generation reflects that exposure. Z-HEALTH is designed to generate the evidence base that European policy needs to protect it.

## The shared exposure pathway: how digital environments drive all three conditions

Digital environments do not merely correlate with poor health outcomes in young people — they are an active causal agent. The mechanism is a habit-formation pathway: repeated digital exposure generates automaticity; automaticity produces habit; habits persist when stabilised by identity and social norms. This pathway operates across all three disease domains through four specific mechanisms, each of which constitutes an intervention target for Z-HEALTH.

i. Hyper-targeted marketing of health-harmful products. Digital platforms enable the marketing of UPF, alcohol, nicotine, and gambling products to young people with a precision, personalisation, and scale that has no historical precedent. Boyland et al. (2022), in a systematic review and meta-analysis of 87 studies, found robust evidence that food and beverage marketing — including digital marketing — is causally associated with children and adolescents' eating behaviours and health outcomes.11 Bragg et al. (2021) demonstrated experimentally that exposure to alcohol advertising on social media increased young adults' alcohol intentions and consumption.12 Montiel et al. (2021) documented the association between online gambling access and adolescent problem gambling.13

ii. Platform design that normalises and eases access to health-harmful content. Infinite scroll, autoplay, notification architectures, and algorithmic content curation are designed to maximise engagement — and engagement with health-harmful content drives health-harmful behaviours. These design features function as exposure amplifiers for all three disease domains: they increase UPF marketing exposure time, extend late-night device use that disrupts sleep, and create the variable reward schedules that underpin gambling and gaming disorder.

iii. Health misinformation that distorts beliefs and perceived norms. Suarez-Lledo & Alvarez-Galvez (2021), in a systematic review of 69 studies, found that health misinformation — including nutritional misinformation, pro-eating-disorder content, and minimisation of alcohol and gambling harms — is prevalent and widely engaged with on social media.14 For young people whose health beliefs are still forming, this misinformation directly shapes the normative landscape that determines whether healthy or unhealthy behaviours feel socially acceptable.

iv. Restructuring of social interaction in ways that harm health. Social media has transformed how young people relate to peers, with consequences for all three disease domains. Screen-mediated social comparison drives body dissatisfaction, disordered eating, and anxiety. Late-night social media use displaces sleep. Social isolation — paradoxically common among heavy social media users — is an independent risk factor for depression, obesity, and addiction. Twenge et al. (2020) documented in Nature Human Behaviour that the magnitude of associations between social media use and adolescent mental health is clinically meaningful and has been systematically underestimated.15 Orben et al. (2022) identified specific developmental windows — ages 11–13 for girls and 14–15 for boys — during which social media sensitivity is greatest.16

## The evidence gap: why effective intervention evidence does not yet exist at the required scale

Despite the scale of the problem, the evidence base for effective behavioural interventions targeting these three disease conditions in 12–25 year-olds, in European settings, at the scale required for population-level impact, remains critically underdeveloped. Four gaps are decisive.

Gap 1: Single-condition trials that miss shared pathways. Existing intervention research is siloed by disease. There are trials for obesity interventions, mental health interventions, and addiction interventions — but no project has simultaneously addressed all three conditions within a common theoretical framework, tested whether interventions targeting shared digital exposure pathways produce cross-condition benefits, or evaluated whether gains on one condition come at the cost of another. Z-HEALTH fills this gap.

Gap 2: Controlled settings that fail to demonstrate real-world scalability. Most existing behavioural intervention trials are conducted in highly controlled settings with atypical populations. They demonstrate proof-of-concept efficacy but not the real-world effectiveness across diverse European cultural, socioeconomic, and regulatory contexts that policymakers need. Z-HEALTH deploys interventions at scale across ≥5 European countries — spanning social-democratic, Mediterranean, and post-socialist welfare contexts — to generate the generalisable evidence the call requires.

Gap 3: No European evaluation of the digital regulatory experiments already underway. France (2023), the United Kingdom (2024), Australia (2024), and Norway have introduced or legislated restrictions on under-16 smartphone and social media access — the largest natural experiments in youth digital environment modification ever conducted. None has been rigorously evaluated for downstream effects on NCD outcomes. These policy experiments are creating staggered implementation timelines across Z-HEALTH consortium countries, providing a unique quasi-experimental platform. Without Z-HEALTH, this evidence opportunity will be lost.

Gap 4: No account of equity and the bundling problem. High-agency behavioural interventions — self-monitoring, goal-setting, digital therapeutics — tend to benefit young people who are already advantaged: those with higher health literacy, greater digital access, and more supportive environments. When deployed without structural protection (low-agency G1/G2 interventions), high-agency interventions can widen health inequalities rather than narrow them. This is the core equity hypothesis that Miraldo's bundling framework addresses — and it has never been tested in the context of digital environment interventions. Z-HEALTH tests it directly.

## Z-HEALTH: an overview

Z-HEALTH — Health in the Digital Generation — is a multi-country Research and Innovation Action that will evaluate, at scale and across diverse European contexts, the effectiveness of evidence-based behavioural interventions for preventing and reducing the burden of obesity, mental health diseases, and addictions in young people aged 12 to 25. It does so by targeting the shared modifiable causal pathway — the digital habit-formation process — through a pre-specified architecture of four complementary intervention families.

The unifying logic model follows a habit forming pathway: Environments → Exposure → Repetition/automaticity → Habit formation → Stabilisation.

Interventions enter at different points in this causal chain, constituting four complementary families: (G1) Exposure shaping — preventing habit formation by reducing harmful digital cues (defaults, marketing restrictions); (G2) Friction and interruption — slowing automatic repetition through speed bumps (quiet hours, age gates, cool-off periods); (G3) Agency scaffolding — rebuilding routines via self-regulation supports and feedback (wearables, goal-setting, commitment devices); (G4) Identity and norm stabilisation — locking in gains through peer norms, co-created identities and autonomy-framed inoculation. No single family is sufficient. Z-HEALTH will be the first project to implement all four families simultaneously within the same theoretical framework, across multiple countries and NCD domains.

The Z-HEALTH Habit Pathway

| ENVIRONMENTS | EXPOSURE | REPETITION / AUTOMATICITY | HABIT FORMATION | STABILISATION (identity/norms) |
| --- | --- | --- | --- | --- |
| Digital, social, institutional | Algorithms, marketing, misinformation | Fast, frictionless, high-frequency | Routine, automatic, rewarding | Peer norms, identity, social signals |
| G1: Exposure shaping | G2: Friction & interruption | G3: Agency scaffolding | G4: Identity / norm stabilisation | Policy uptake & scale-out |

Figure 1: The Z-HEALTH habit pathway and corresponding intervention families [Source?]

### The G1–G4 intervention framework

The G1–G4 framework is the primary organising architecture of Z-HEALTH. Every work package, every study design, and every partner role is structured around these four intervention families, applied across all three disease conditions. The framework is not new in concept — it synthesises Miraldo's bundling logic, Verplanken's habit discontinuity hypothesis, and the growing literature on structural versus empowerment approaches to behaviour change — but Z-HEALTH is the first project to operationalise all four families simultaneously across multiple NCDs, multiple countries, and multiple life-stage windows.

|  | G1 — Exposure Shaping Prevent habits forming by reducing harmful digital cues | G2 — Friction & Interruption Slow automatic repetition through design speed-bumps | G3 — Agency Scaffolding Rebuild routines via self-regulation, feedback, tools | G4 — Identity/Norm Stabilisation Lock in gains through peer norms and co-created identities |
| --- | --- | --- | --- | --- |
| Agency required | None (structural) | Low (design nudge) | Moderate (self-regulation) | High (identity/social) |
| Obesity | UPF marketing restrictions (DSA natural experiments); front-of-pack label defaults; school food environment redesign; smartphone ban evaluation → dietary behaviour | Cafeteria choice architecture (default healthy options); checkout friction in food delivery apps; quiet hours reducing late-night snacking cues | Wearable dietary + PA self-monitoring; food transparency apps (Yuka, Open Food Facts); goal-setting + implementation intentions; incentive/commitment devices | Peer norm reinforcement for healthy food choices; prebunking/inoculation against UPF marketing manipulation; co-created food norms with youth cohorts |
| Mental Health Diseases | Platform sleep-mode defaults; notification batch architecture; smartphone/social media ban evaluation → sleep quality, depression/anxiety; pagination disrupting body-image social comparison | Screen-time self-monitoring + CBT-I combined package; platform sleep-mode tools vs. third-party blockers (Opal RCT); once-daily notification batching | Computerised CBT (cCBT) for anxiety/depression; wearable sleep monitoring + feedback; mindfulness apps (validated protocols); transition-timed CBT-I deployment | Co-created mental health help-seeking norms; inoculation against social comparison and body-image triggers; peer support network design |
| Addictions | Gambling/vaping advertising restriction evaluation (DSA/AVMSD compliance across ≥3 EU countries); age-gate enforcement at digital point of exposure; influencer content regulation | Mandatory cool-off/reflection prompts in gambling apps; temporary self-exclusion tools; vaping device usage friction; reduced autoplay in addiction-promoting content | e-Brief interventions (e-BI) + personalised normative feedback for alcohol (ages 18–25; Kaner et al. Cochrane base); digital CBT for substance use; vaping/gaming self-monitoring | Peer norm campaigns against vaping/gambling initiation; identity-based prebunking against addiction marketing; community-level norm activation |

Table 1. G1–G4 intervention families mapped across the three disease conditions. All interventions are evidence-based at TRL ≥5 at project entry. Full TRL table in Section 1.1.4.

### Life-course transitions as effect modifiers

A key differentiator of Z-HEALTH is the treatment of life-course transitions as planned effect modifiers, not merely demographic controls. Transitions weaken existing habits (increasing plasticity) but often reduce available agency — conditions under which purely informational or high-effort interventions are inequitable and prone to decay. Z-HEALTH operationalises this insight across three strata:

| Age stratum | Transition context | Effective intervention families |
| --- | --- | --- |
| 12–15 (early adolescence) | Shared school/family environments; peer groups highly influential; digital habits forming rapidly | G1 Exposure shaping + G4 Identity/norm stabilisation work well: environments are shared and enforceable |
| 15–18 (late school) | Autonomy increases; exam stress peaks; timing displacement (late-night digital use) prominent; new habits forming | G2 Friction + G3 Agency scaffolding critical: protect routines and support self-regulation under stress |
| 18–25 (post-school transition) | Major environment change (HE, work, independent living); routines collapse; commercial exposure high; new identities forming | G2 Low-agency protection + G3 Agency scaffolding + G4 Identity reinforcement needed to lock in habits as routines stabilise |

## Project objectives

Z-HEALTH has five SMART objectives, each linked to the three disease conditions and the G1–G4 framework:

| Obj. | Description | Verifiable indicators |
| --- | --- | --- |
| O1 | Select, adapt and bundle evidence-based interventions covering all three disease conditions and all four G-families. Drawing on a systematic review (all components TRL ≥5) and youth co-creation in ≥5 countries, adapt interventions for each disease condition and each G-family, and develop bundling protocols requiring ≥1 low-agency (G1+G2) and ≥1 high-agency (G3+G4) component per site — ensuring structural protection accompanies empowerment. Primary outcome anchors pre-specified: BMI z-score/dietary quality (obesity); PHQ-9, GAD-7, PSQI (mental health diseases); AUDIT-C, PGSI, Fagerström (addictions). | Systematic review and intervention map (M6); adaptation frameworks validated with youth (M12); ≥8 bundled interventions ready across all three disease conditions (M12) |
| O2 | Implement pre-specified intervention bundles in powered, pre-registered field experiments across ≥5 European countries. Cluster-RCTs, RCTs, and quasi-experimental natural experiments. Exploit life-course transition windows as planned strata. Primary endpoints are disease-specific clinical measures — not behaviour proxies alone — for all three conditions. | ≥5 country sites active (M18); ≥3,000 young people enrolled across three disease conditions (M24); end-of-intervention + 12-month follow-up data (M48) |
| O3 | Test the equity hypothesis: do G3/G4 high-agency interventions widen inequalities unless paired with G1/G2 structural protection? Comparative effectiveness analysis across all three disease conditions, stratified by SES, gender, and migration background, exploiting natural variation in the EU digital regulatory environment. Direct operationalisation of Miraldo's bundling logic. | Comparative effectiveness analysis for ≥3 condition/mechanism combinations (M48); equity moderation analysis (M48); policy brief (M54) |
| O4 | Model the long-term disease burden impact of scaling the most effective interventions, and forecast future digital exposure pathways. Health-GPS microsimulation (Imperial/CHEPI) will project 10-year disease burden reduction and cost-effectiveness scenarios for all three conditions at national and EU level. ISINNOVA foresight methods will anticipate how digital environments will evolve over 10–15 years and identify next-generation exposure pathways, ensuring recommendations remain policy-relevant. | Health-GPS scale-up scenarios per condition (M42); cost-effectiveness analysis (M48); ISINNOVA foresight report — 2035 youth NCD exposure scenarios (M48) |
| O5 | Translate findings into condition-specific, policy-ready evidence for EU and national regulators. Policy toolkits for all three disease conditions in ≥4 languages. Direct policy reinforcement pathway to DSA Article 28, AVMSD implementation, and national NCD prevention strategies. Formats for collaboration between healthcare professionals, educators, and policymakers. | Policy recommendations submitted to ≥3 EU/national processes (M54); toolkits in ≥4 languages (M54); ≥20 peer-reviewed publications (M60) |

### Beyond the state of the art

First, integration of three disease conditions within one framework. No prior project has simultaneously targeted obesity-as-disease, mental health diseases as a family, and addictions-as-disease within a single causal model and intervention architecture. The shared digital habit-formation pathway means cross-disease synergies are theoretically predicted and empirically testable — and Z-HEALTH is the first project to test them.

Second, the G1–G4 bundle architecture across the full agency spectrum. The NCD prevention literature is divided between regulatory/structural interventions and individual empowerment interventions, with the equity consequences of this split poorly understood. No prior project has simultaneously implemented all four G-families within the same theoretical framework. The pre-specified primary equity analysis of bundled versus unbundled interventions is a first.

Third, life-course transition targeting. Z-HEALTH operationalises life-course transitions (ages 12–15, 15–18, 18–25) as planned effect modifiers grounded in Verplanken & Roy's Habit Discontinuity Hypothesis17 and Lally et al.'s finding that habits form in as few as 66 days.18 Z-HEALTH is the first project to exploit the ~3-month disruption window simultaneously across multiple transitions, multiple countries, and multiple NCD domains.

Fourth, evaluation of the digital regulatory natural experiments. France, the UK, Australia, and Norway have created the largest natural experiments in youth digital environment modification ever conducted. None has been evaluated for downstream NCD outcomes. Z-HEALTH's consortium spans countries with different and staggered implementation timelines, enabling quasi-experimental evaluation using difference-in-differences designs that will generate first-in-field causal evidence on the NCD consequences of macro-level digital regulation.

Fifth, Health-GPS policy simulation and ISINNOVA foresight. Imperial College's Centre for Health Economics & Policy Innovation (CHEPI) will use the Health-GPS open-source microsimulation platform to project the 10-year disease burden reduction achievable through scaling Z-HEALTH's most effective interventions — translating trial evidence into the population-level estimates that health ministries need to make investment decisions. ISINNOVA's structured foresight work will produce 2035 scenarios for youth NCD digital exposure that ensure recommendations remain relevant as digital environments continue to evolve.

## Overview of the methodological approach

Z-HEALTH's methodology is organised around the three disease conditions as primary anchors. This is not a single-method study: it is a coordinated programme of eight complementary field experiments — cluster-randomised controlled trials, individually randomised controlled trials, and quasi-experimental natural experiments — that together provide converging evidence on which G1–G4 interventions reduce the burden of obesity, mental health diseases, and addictions in 12–25 year-olds across diverse European contexts.

Three design principles govern all studies. First, clinical disease endpoints are primary — BMI z-score, PHQ-9, AUDIT-C — not behaviour proxies alone. Second, all trials are pre-registered (ISRCTN or ClinicalTrials.gov) before data collection begins. Third, life-course transition windows (primary→secondary school; secondary→higher education/work) are exploited as planned strata in all age-eligible studies, based on the Habit Discontinuity Hypothesis: transitions create ~3-month windows of behavioural plasticity during which new patterns can be established in as few as 66 days.1,2

All eight studies deploy wearable and digital self-monitoring tools as both intervention components and measurement instruments, using interoperable consumer-grade devices (Fitbit Charge 6, Garmin Vivosmart 5, ActiGraph GT9X) and OS-level tools (iOS Screen Time API, Android Digital Wellbeing), in line with the call's requirements for user-friendly, interoperable hardware. AI-assisted personalisation of G3 components is implemented using federated machine learning approaches that do not require centralised personal data transfer. Real-world data (RWD) from national health registries (UCopenhagen, NIPH) are linked to trial data in ≥3 countries for population-level effectiveness evaluation.

### Study programme overview

| Study | Design | Condition(s) | G-family | n / Ages / Countries | Primary disease endpoint(s) | Lead |
| --- | --- | --- | --- | --- | --- | --- |
| S1 | Cluster-RCT | Obesity | G1 + G2 | n≥1,200 / 12–16 yrs / Denmark, Norway, Slovenia | BMI z-score; NOVA dietary quality; PA (accelerometry) | UCopenhagen (lead) |
| S2 | 3-arm RCT | Obesity | G1 + G2 | n≥800/arm / 13–17 yrs / ≥4 EU countries | UPF purchasing; BMI z-score; body image (BESAA) | NYU/Bragg (lead); ICL; UCopenhagen |
| S3 | RCT | Obesity | G3 | n≥600 / 14–25 yrs / ≥3 EU countries | UPF substitution rate; Nutri-Score; dietary quality | ICL/Sassi (lead); UCopenhagen; NIJZ |
| S4 | 3-arm RCT | Mental Health | G2 + G3 | n≥350 / 13–17 yrs / ≥3 EU countries | PSQI score; actigraphy sleep duration/quality | NYU/Bragg (lead); ICL; NIJZ |
| S5 | RCT (transition-timed) | Mental Health + Obesity | G2 + G3 | n≥500 / 17–20 yrs / ≥3 EU countries | PSQI; PHQ-9; GAD-7; (secondary) dietary change at transition | UoCologne/EBEH (lead); NIJZ; ICL |
| S6 | Controlled trial | Mental Health | G3 | n≥400 / 16–22 yrs / Slovenia, Norway | PHQ-9; GAD-7; cortisol reactivity; actigraphy | NIJZ (lead); NIPH; UoCologne |
| S7 | RCT | Addictions | G3 | n≥600 / 18–25 yrs / ≥3 EU countries | AUDIT-C; alcohol use frequency; binge episodes | ICL/Sassi (lead); UoCologne; UCopenhagen |
| S8 | Quasi-experimental (staggered DiD) | All 3 conditions | G1 (macro) | Population-level / 12–25 yrs / ≥4 EU + Australia, UK | BMI; PHQ-9; AUDIT-C; PGSI; Fagerström — registry-linked | UCopenhagen (lead); ICL; NIPH; EuroHealthNet |

Table 2. Z-HEALTH study programme overview. DiD = difference-in-differences. BESAA = Body Esteem Scale for Adolescents and Adults. UPF = ultra-processed food. All sample sizes are minimum targets; power calculations detailed per study below.

## Work package list [DRAFT]

| WP | Title | Indicative Lead |
| --- | --- | --- |
| WP1 | Project Coordination & Management Overarching across all WPs | ICL (Franco Sassi) All partners |
| WP2 | Ethics | ICL / designated Ethics Officer |
| WP3 | NCD Evidence Framework & Disease Context Obesity · Mental Health · Addictions | ICL (Sassi) Partner disease leads |
| WP4 | Intervention Design Lower Secondary School (ages 12–15) | NIPH (Norway) or UCopenhagen |
| WP5 | Intervention Design Upper Secondary School (ages 16–18, +transition) | NIJZ (Slovenia) or UCopenhagen |
| WP6 | Implementation Field delivery across partner countries | National Public Health Institutes (country leads) |
| WP7 | Evaluation Cross-cutting horizontal WP | TBC (independent evaluation lead) |
| WP8 | Modelling & Foresight Cross-cutting horizontal WP | ICL/CHEPI (Sassi) + ISINNOVA |
| WP9 | Dissemination & Exploitation Cross-cutting horizontal WP | EuroHealthNet (lead) + ICL |

### References

1. Sawyer SM et al. Adolescence: a foundation for future health. Lancet. 2012;379(9826):1630–1640. doi:10.1016/S0140-6736(12)60072-5 [PMID:22538178]

2. Buoncristiano M et al. Childhood overweight and obesity in Europe: Changes from 2007 to 2017. Obesity Reviews. 2021;22(S6):e13226. doi:10.1111/obr.13226 [PMID:34378305]

3. Garrido-Miguel M et al. Prevalence and Trends of Overweight and Obesity in European Children From 1999 to 2016: A Systematic Review and Meta-analysis. JAMA Pediatrics. 2019;173(10):e192430. doi:10.1001/jamapediatrics.2019.2430 [PMID:31381031]

4. Monteiro CA et al. Ultra-processed foods: what they are and how to identify them. Public Health Nutrition. 2019;22(5):936–941. doi:10.1017/S1368980018003762

5. Castelpietra G et al. The burden of mental disorders, substance use disorders and self-harm among young people in Europe, 1990–2019: Findings from the Global Burden of Disease Study 2019. Lancet Regional Health – Europe. 2022;16:100341. doi:10.1016/j.lanepe.2022.100341 [PMID:35392452]

6. McGorry PD et al. The Lancet Psychiatry Commission on youth mental health. Lancet Psychiatry. 2024;11(9):731–774. doi:10.1016/S2215-0366(24)00163-9 [PMID:39147461]

7. Carter B et al. Association Between Portable Screen-Based Media Device Access or Use and Sleep Outcomes: A Systematic Review and Meta-analysis. JAMA Pediatrics. 2016;170(12):1202–1208. doi:10.1001/jamapediatrics.2016.2341 [PMID:27802500]

8. WHO Regional Office for Europe. WHO European Region has the highest rate of tobacco use in the world, with an alarming rise in young people using e-cigarettes. 2025. Available at: https://www.who.int/europe/news/item/08-10-2025

9. Tarasenko Y et al. Electronic cigarette use among adolescents in 17 European study sites: findings from the Global Youth Tobacco Survey. European Journal of Public Health. 2022;32(S1):i51–i56. [PMID:34694383]

10. Calado F, Alexandre J, Griffiths MD. Prevalence of Adolescent Problem Gambling: A Systematic Review of Recent Research. Journal of Gambling Studies. 2017;33(2):397–424. doi:10.1007/s10899-016-9627-5 [PMID:27372832]

11. Boyland EJ et al. Association of Food and Nonalcoholic Beverage Marketing With Children and Adolescents' Eating Behaviors and Health: A Systematic Review and Meta-analysis. JAMA Pediatrics. 2022;176(7):e221037. doi:10.1001/jamapediatrics.2022.1037 [PMID:35499839]

12. Bragg MA et al. Marketing alcoholic beverages to young adults on social media: a content analysis. Journal of Medical Internet Research. 2021;23(10):e28689. doi:10.2196/28689 [PMID:34677136]

13. Montiel I et al. Problematic online gambling among adolescents: A systematic review about prevalence and related measurement issues. Journal of Behavioral Addictions. 2021;10(3):566–586. [PMID:34550906]

14. Suarez-Lledo V & Alvarez-Galvez J. Prevalence of Health Misinformation on Social Media: Systematic Review. Journal of Medical Internet Research. 2021;23(1):e17187. doi:10.2196/17187 [PMID:33470931]

15. Twenge JM, Haidt J, Joiner TE, Campbell WK. Underestimating digital media harm. Nature Human Behaviour. 2020;4(4):346–348. doi:10.1038/s41562-020-0839-4 [PMID:32303719]

16. Orben A, Przybylski AK, Blakemore S-J, Kievit RA. Windows of developmental sensitivity to social media. Nature Communications. 2022;13:1649. doi:10.1038/s41467-022-29296-3

17. Verplanken B & Roy D. Empowering interventions to promote sustainable lifestyles. Journal of Environmental Psychology. 2016;45:163–174. doi:10.1016/j.jep.2016.01.001

18. Lally P et al. How are habits formed: Modelling habit formation in the real world. European Journal of Social Psychology. 2010;40(6):998–1009. doi:10.1002/ejsp.674

19. Noel JK et al. Alcohol marketing on social media: a systematic review. Journal of Studies on Alcohol and Drugs Supplement. 2020;s19:57–67. doi:10.15288/jsads.2020.s19.57

20. Kaner EFS et al. Personalised digital interventions for reducing hazardous and harmful alcohol consumption in community-dwelling populations. Cochrane Database of Systematic Reviews. 2018;2:CD011479. doi:10.1002/14651858.CD011479.pub2

21. Roozenbeek J et al. Psychological inoculation improves resilience against misinformation on social media. Science Advances. 2022;8(34):eabo6254. doi:10.1126/sciadv.abo6254 [PMID:36001675]

22. Cadario R & Chandon P. Which healthy eating nudges work best? A meta-analysis of field experiments. Marketing Science. 2020;39(3):465–486. doi:10.1287/mksc.2019.1185

23. Orben A & Przybylski AK. The association between adolescent well-being and digital technology use. Nature Human Behaviour. 2019;3(2):173–182. doi:10.1038/s41562-018-0506-1 [PMID:30944443]

24. Sassi F et al. Equity impacts of price policies to promote healthy behaviours. Lancet. 2018;391(10134):2059–2070. doi:10.1016/S0140-6736(18)30531-2 [PMID:29627166]

25. Hale L & Guan S. Screen time and sleep among school-aged children and adolescents: A systematic literature review. Sleep Medicine Reviews. 2015;21:50–58. doi:10.1016/j.smrv.2014.07.007 [PMID:25193149]

1.2	Methodology

14 PAGES

| Contribution from WP8 | Foresight in Z-HEALTH is implemented as a structured, participatory, and policy-oriented process to anticipate how youth health behaviours and their relatedkey drivers may evolve over the next 10–20 years, and how behavioural interventions for NCD prevention may need to adapt in response. The approach builds on ISINNOVA’s extensive expertise in EU policy-oriented foresight, including the Foresight on Demand (FOD) framework, and adapts a methodology tested in a previous EU project ( EUARENAS), combining social media signal scanning, participatory sense-making, and Delphi-inspired foresight rounds. The methodology is grounded in continuous engagement with youth and expert stakeholders. A Youth Advisory Committee ensures continuous engagement of diverse youth groups, contributing to the identification and interpretation of emerging trends, validation of findings, and assessment of intervention relevance and acceptability. These participatory inputs will be complemented by the involvement of multidisciplinary experts from public health, behavioural science, digital media, policy, education, and civil society. The foresight cycle includes: (i) systematic analysis of social media and other sources to detect emerging behaviours, attitudes, and inequalities; (ii) collective interpretation by a multidisciplinary panel to identify trends, mismatches with intervention assumptions, and early warning signals; and (iii) prioritisation of key uncertainties and assessment of intervention robustness across youth segments. Foresight outputs feed into scenario development and subsequent modelling and policy simulation, nabling the project to assess the long-term effectiveness, equity, scalability, and robustness of interventions under alternative future conditions. |
| --- | --- |

1.2.1 OVERALL METHODOLOGY (10 pages)

Describe and explain the overall methodology, including the concepts, models and assumptions that underpin your work. Explain how this will enable you to deliver your project’s objectives. Refer to any important challenges you may have identified in the chosen methodology and how you intend to overcome them.

- This section should be presented as a narrative. The detailed tasks and work packages are described below under ‘Implementation’.

Insert here text for your proposal

1.2.2 BACKGROUND (1 page)

Describe any national or international research and innovation activities whose results will feed into the project, and how that link will be established

| Contribution from WP8 | ISINNOVA will leverage its experience as active member of the European Commission’s Foresight-on-Demand (FOD) consortium and the expertise matured in the development of participatory foresight processes (scenarios, Delphi surveys, stakeholder workshops), alongside contributions to the Futures4Europe platform. This experience will ensure methodological robustness, alignment with EU foresight standards and fruitfulconnections with ongoing foresight initiatives. Z-HEALTH will also benefit from ISINNOVA’s experience in health-related foresight projects, notably FRESHER and Rare2030, which developed participatory scenarios and long-term policy recommendations in complex health domains. Z-HEALTH advances beyond these initiatives by integrating foresight directly with the implementation,evaluation and policy simulation of behavioural interventions targeting youth. Further synergies will be established with EU foresight and policy communities, including the European Strategic Foresight Network and the JRC Foresight Competence Centre, as well as relevant health and innovation ecosystems (e.g. EIT Health). Knowledge exchange will be ensured through partners’ networks, joint dissemination, and reuse of methods and insights, ensuring complementarity, avoiding duplication, and enhancing policy relevance to position Z-HEALTH within the wider European anticipatory policy landscape. |
| --- | --- |

Insert here text for your proposal

1.2.3. INTERDISCIPLINARITY APPROACH (1/2 page)

Explain how expertise and methods from different disciplines will be brought together and integrated in pursuit of your objectives. If you consider that an inter-disciplinary approach is unnecessary in the context of the proposed work, please provide a justification

Insert here text for your proposal

1.2.4 SOCIAL SCIENCES AND HUMANITIES (1/2 page)

For topics where the work programme indicates the need for the integration of social sciences and humanities, show the role of these disciplines in the project or provide a justification if you consider that these disciplines are not relevant to your proposed project.

Insert here text for your proposal

1.2.5 GENDER DIMENSION (1 page)

Describe how the gender dimension (i.e. sex and/or gender analysis) is taken into account in the project’s research and innovation content. If you do not consider such a gender dimension to be relevant in your project, please provide a justification.

Note: This section is mandatory except for topics which have been identified in the work programme as not requiring the integration of the gender dimension into R&I content.

Remember that that this question relates to the content of the planned research and innovation activities, and not to gender balance in the teams in charge of carrying out the project.

Sex and gender analysis refers to biological characteristics and social/cultural factors respectively. For guidance on methods of sex / gender analysis and the issues to be taken into account, please refer to https://op.europa.eu/en/publication-detail/-/publication/33b4c99f-2e66-11eb-b27b-01aa75ed71a1/language-en

Insert here text for your proposal

1.2.6 OPEN SCIENCE (1 page)

Describe how appropriate open science practices are implemented as an integral part of the proposed methodology. Show how the choice of practices and their implementation are adapted to the nature of your work, in a way that will increase the chances of the project delivering on its objectives [e.g. 1 page]. If you believe that none of these practices are appropriate for your project, please provide a justification here.

- Open science is an approach based on open cooperative work and systematic sharing of knowledge and tools as early and widely as possible in the process. Open science practices include early and open sharing of research (for example through preregistration, registered reports, pre-prints, or crowd-sourcing); research output management; measures to ensure reproducibility of research outputs; providing open access to research outputs (such as publications, data, software, models, algorithms, and workflows); participation in open peer-review; and involving all relevant knowledge actors including citizens, civil society and end users in the co-creation of R&I agendas and contents (such as citizen science).

- Please note that this question does not refer to outreach actions that may be planned as part of communication, dissemination and exploitation activities. These aspects should instead be described below under ‘Impact’.

- Proposals selected for funding under Horizon Europe will need to develop a detailed data management plan (DMP) for making their data/research outputs findable, accessible, interoperable and reusable (FAIR) as a deliverable by month 6 and revised towards the end of a project’s lifetime. The DMP should describe how research outputs (especially research data) generated and/or collected during the project will be managed so as to ensure that they are findable, accessible, interoperable and reusable.

- For guidance on open science practices and research data management, please refer to the relevant section of the HE Programme Guide on the Funding & Tenders Portal.

Insert here text for your proposal

- Impact

Impact – aspects to be taken into account. - Credibility of the pathways to achieve the expected outcomes and impacts specified in the work programme, and the likely scale and significance of the contributions due to the project. - Suitability and quality of the measures to maximise expected outcomes and impacts, as set out in the dissemination and exploitation plan, including communication activities.

The results of your project should make a contribution to the expected outcomes set out for the work programme topic over the medium term, and to the wider expected impacts set out in the ‘destination’ over the longer term.

In this section you should show how your project could contribute to the outcomes and impacts described in the work programme, the likely scale and significance of this contribution, and the measures to maximise these impacts.

2.1	Project’s pathways towards impact

3 PAGES

Provide a narrative explaining how the project’s results are expected to make a difference in terms of impact, beyond the immediate scope and duration of the project. The narrative should include the components below, tailored to your project.

- Describe the unique contribution your project results would make towards (1) the outcomes specified in this topic, and (2) the wider impacts, in the longer term, specified in the respective destinations in the work programme. Provide quantified estimates where possible and meaningful.

- Be specific, referring to the effects of your project, and not R&I in general in this field.

State the target groups that would benefit. Even if target groups are mentioned in general terms in the work programme, you should be specific here, breaking target groups into particular interest groups or segments of society relevant to this project.

- Describe any requirements and potential barriers - arising from factors beyond the scope and duration of the project - that may determine whether the desired outcomes and impacts are achieved. These may include, for example, other R&I work within and beyond Horizon Europe; regulatory environment; targeted markets; user behaviour. Indicate if these factors might evolve over time. Describe any mitigating measures you propose, within or beyond your project, that could be needed should your assumptions prove to be wrong, or to address identified barriers.

- Note that this does not include the critical risks inherent to the management of the project itself , which should be described below under ‘Implementation’.

Insert here text for your proposal

2.2	Measures to maximise impact - Dissemination, exploitation and communication

3 PAGES EXCLUDING SECTION 2.3

Describe the planned measures to maximise the impact of your project by providing a first version of your ‘plan for the dissemination and exploitation including communication activities’. Describe the dissemination, exploitation and communication measures that are planned, and the target group(s) addressed (e.g. scientific community, end users, financial actors, public at large).

- Please remember that this plan is an admissibility condition, unless the work programme topic explicitly states otherwise. In case your proposal is selected for funding, a more detailed ‘plan for dissemination and exploitation including communication activities’ will need to be provided as a mandatory project deliverable within 6 months after signature date. This plan shall be periodically updated in alignment with the project’s progress.

- Communication measures should promote the project throughout the full lifespan of the project. The aim is to inform and reach out to society and show the activities performed, and the use and the benefits the project will have for citizens. Activities must be strategically planned, with clear objectives, start at the outset and continue through the lifetime of the project. The description of the communication activities needs to state the main messages as well as the tools and channels that will be used to reach out to each of the chosen target groups.

- All measures should be proportionate to the scale of the project, and should contain concrete actions to be implemented both during and after the end of the project, e.g. standardisation activities. Your plan should give due consideration to the possible follow-up of your project, once it is finished. In the justification, explain why each measure chosen is best suited to reach the target group addressed. Where relevant, and for innovation actions, in particular, describe the measures for a plausible path to commercialise the innovations.

- If exploitation is expected primarily in non-associated third countries, justify by explaining how that exploitation is still in the Union’s interest.

- Describe possible feedback to policy measures generated by the project that will contribute to designing, monitoring, reviewing and rectifying (if necessary) existing policy and programmatic measures or shaping and supporting the implementation of new policy initiatives and decisions.

Outline your strategy for the management of intellectual property, foreseen protection measures, such as patents, design rights, copyright, trade secrets, etc., and how these would be used to support exploitation.

- If your project is selected, you will need an appropriate consortium agreement to manage (amongst other things) the ownership and access to key knowledge (IPR, research data etc.). Where relevant, these will allow you, collectively and individually, to pursue market opportunities arising from the project.

- If your project is selected, you must indicate the owner(s) of the results (results ownership list) in the final periodic report.

Insert here text for your proposal

Z-Health’s pathway to impact will be guided by a strategic Dissemination, Exploitation and Communication (DEC) plan, built on the following principles:

- Collaboration: All Z-Health project partners will play a role in communication, dissemination, and exploitation activities. The DEC plan (Dxx, by M6?) will provide all partners with guidance on how to communicate about the project and its results in a coherent and consistent way, while drawing on partners’ complementary expertise, networks, and national or local and contextual knowledge relevant to reaching key audiences and supporting uptake of results. Alongside the project's other governance structures, a DEC coordination group bringing together one representative from each partner will meet regularly to support effective internal coordination and external communication of Z-Health activities and findings. The Z-Health consortium will also actively connect with other relevant EU-funded projects, initiatives and networks in related fields to maximise synergies, visibility and mutual learning.

- Consultation and co-creation: Relevant target groups (as further described below) will be consulted and involved in the design, refinement and validation of key project activities and outputs, including intervention-related materials, communication products, practice-oriented resources and policy messages. This is particularly important in a project working with older adolescents and young adults, where relevance, acceptability and accessibility of approaches and messages are essential to successful engagement and uptake. Consulting key stakeholders from the outset will strengthen ownership, applicability, relevance and potential for uptake and transfer of Z-Health results.

- Continuity and sustainability: Communication, dissemination and exploitation planning and activities will take place throughout the project lifetime. The DEC plan will be routinely reviewed and updated to ensure the continuing relevance, quality and attractiveness of Z-Health’s communication and dissemination approaches and tools. Progress against the indicators set out in the plan will be monitored regularly and reviewed at least annually. Exploitation activities will increasingly come into focus in the later stages of the project and will support the longer-term use, transferability and sustainability of Z-Health findings, tools and recommendations beyond the funded period.

- Targeted and tailored approaches: Communication, dissemination and exploitation activities, including messaging, will be carefully tailored to ensure that they resonate with their respective audiences, such as researchers, policymakers, public health actors, practitioners, civil society organisations, youth-serving organisations, and representatives of older adolescents and young adults, including those in vulnerable situations or at greater risk of exclusion. Outreach will be grounded in stakeholder mapping, to be initiated at the start of the project, and in an understanding of the relevant policy, practice and implementation landscapes at European, national and where relevant local level. As feasible, project outputs and messages will be adapted to different national contexts and made accessible in a range of relevant EU languages. To maximise impact, messages will be shared through a mix of channels and formats suited to different audiences, thereby increasing their reach, accessibility and potential use.

More details on specific communication, dissemination and exploitation activities, key target audiences, tools and channels are provided below, as well as in the WP9 description. This work package will follow a logical sequence: establishing the foundations for project-wide communication and dissemination; positioning Z-Health within the relevant stakeholder and policy landscape; supporting the dissemination of emerging findings and interaction with key stakeholders throughout implementation; and preparing the exploitation, uptake and longer-term use of Z-Health results beyond the lifetime of the project. In line with the project’s health equity orientation, Z-Health will aim for inclusive, accessible and gender-balanced engagement across all communication, dissemination and exploitation activities, while remaining responsive to the diversity of young people’s circumstances and the changing demographic realities of European societies.

Target groups: Z-Health will focus on two broad and interlinked target groups, aligned with the project’s objectives. The first includes stakeholders who can generate, apply, support or scale up the project’s results, such as researchers, policymakers, public health actors, practitioners, education and community organisations, and other relevant intermediaries. The second includes the wider public, with a particular focus on older adolescents and young adults, including those in vulnerable situations or at greater risk of exclusion, who are both a key audience for and, where relevant, contributors to the project.

These stakeholder groups can be further differentiated:

- Research and scientific communities are important for ensuring the visibility, credibility and further development of Z-Health findings. This includes experts in areas such as youth health, public health, mental health, health behaviours, nutrition and obesity, substance use, prevention, implementation science, and health equity.

- Decision-makers and policymakers are a key target group for supporting the uptake of Z-Health results in policy and systems change. These actors operate at local, regional, national and European levels and include public authorities and other bodies with responsibility for youth health, wellbeing, prevention and related services.

- Practice and implementation stakeholders are also central. These include health and care professionals, education and training providers, youth workers, community organisations, social services and civil society actors working with older adolescents and young adults. Their engagement is essential to ensure that Z-Health results are practical, relevant and usable in real-world settings.

- Older adolescents and young adults themselves, including those in vulnerable situations, are a particularly important target group. Z-Health will seek to involve their perspectives, where appropriate, in communication, dissemination and engagement activities, to strengthen the relevance, accessibility and longer-term uptake of project results.

Communication

| Communication – Aims, Measures, and Performance Indicators (M&PI) |  |  |
| --- | --- | --- |
| Overall aim | To communicate and disseminate Z-Health’s work effectively, engage relevant stakeholders, and support the uptake of effective, health-equity-sensitive interventions for older adolescents and young adults. |  |
| Overall M&PI | A shared visual identity for Z-Health, including logo, templates and core communication materials | KPI: Branding package in place by M6 |
|  | A project website with public information on Z-Health, news and updates, and a section for key outputs and resources | KPI: Website launched by M6 |
|  | Project-level communication channels used regularly to share activities, milestones and results | KPI: Regular communication activity throughout M1–M30 |
|  | A Dissemination, Exploitation and Communication (DEC) plan to guide messages, audiences, tools and monitoring | KPI: DEC plan completed by M6 and updated as needed |
|  | An initial stakeholder mapping and engagement framework to support targeted outreach at EU, national and local levels | KPI: Stakeholder mapping completed by M9 |
| Research and scientific communities |  |  |
| Aim | To ensure visibility and credibility of Z-Health within the scientific community and support further development and uptake of project findings. |  |
| M&PI | Present Z-Health concepts, methods and findings at relevant scientific conferences and expert events | KPI: 6–10 conference presentations across the project lifetime |
|  | Disseminate scientific outputs, including methodological papers, protocols and key findings, where relevant | KPI: Scientific dissemination targets to be refined in line with the final research design |
|  | Engage with related EU-funded projects and research initiatives in relevant fields to exchange knowledge and maximise synergies (for instance, reaching out through the EuroHealthNet Partnership of public health authorities across Europe) | KPI: At least 2–4 structured exchanges during the project lifetime |
|  | Use partners’ academic and professional networks to broaden the reach of project findings | KPI: Ongoing outreach through consortium networks across M1–M30 |
| Decision-makers and policymakers |  |  |

| Aim | To position Z-Health as a relevant source of evidence and practical insight for decision-makers and policymakers working on youth health, wellbeing, prevention and health equity. |  |
| --- | --- | --- |
| M&PI | Develop and share policy-oriented messages and outputs tailored to European, national and, where relevant, local audiences | KPI: At least 3–5 policy-facing outputs across the project lifetime |
|  | Present Z-Health findings in policy dialogues, roundtables, stakeholder briefings and relevant events | KPI: Regular participation in policy-relevant events from Year 1 onwards |
|  | Contribute, where feasible, to relevant policy discussions, consultations and strategic processes at EU and national levels | KPI: Strategic policy engagement opportunities identified and acted upon throughout the project |
|  | Build links with relevant EU and national initiatives, frameworks and networks to support visibility and uptake of Z-Health results | KPI: Collaboration and alignment activities maintained across the project period |
| Practice and implementation stakeholders |  |  |
| Aim | To engage actors who can help apply, adapt and support the implementation of Z-Health approaches and findings in real-world settings. |  |
| M&PI | Develop and disseminate practice-oriented materials tailored to relevant implementation settings and intermediaries | KPI: Practice-oriented outputs produced at key project stages |

|  | Engage practitioners and intermediaries through webinars, workshops, peer-learning activities and targeted events | KPI: At least 3–6 stakeholder engagement activities across the project lifetime |
| --- | --- | --- |
|  | Use consortium and stakeholder networks to reach relevant health, education, youth, social and community-based actors | KPI: Multi-sectoral outreach implemented across participating countries and at EU level |
|  | Gather feedback from practice stakeholders to improve the relevance and usability of outputs | KPI: Stakeholder feedback mechanisms integrated into project activities by mid-project |
| Older adolescents and young adults, including those in vulnerable situations |  |  |
| Aim | To ensure that Z-Health is visible, relevant and accessible to older adolescents and young adults, including those in vulnerable situations, and that their perspectives help inform project outreach and uptake. |  |
| M&PI | Develop accessible, audience-appropriate messages and materials tailored to older adolescents and young adults | KPI: Youth-oriented communication materials developed during the project |
|  | Involve relevant youth-facing organisations, networks and, where appropriate, representatives of young people in communication and engagement activities | KPI: Youth engagement mechanisms established by M12 |
|  | Use digital and other appropriate channels to share project messages in formats suitable for younger audiences | KPI: Youth-relevant outreach activities implemented throughout M1–M30 |

|  | Ensure communication approaches reflect health equity, inclusion and accessibility principles | KPI: Equity-sensitive communication principles embedded across project outputs and outreach |
| --- | --- | --- |
| General public |  |  |
| Aim | To make Z-Health, its objectives, activities and key findings known to the wider public, and to raise awareness of the importance of effective and equitable approaches to improving health and wellbeing among older adolescents and young adults. |  |
| M&PI | Share project updates and major results through media outreach, partner channels, press materials and public-facing digital communication | KPI: Public communication activities delivered at major project milestones |
|  | Produce clear and accessible public-facing messages on the relevance and findings of the project | KPI: Public-facing outputs published throughout the project lifetime |
|  | Support visibility of Z-Health through partner organisations’ events, channels and networks | KPI: Consortium-wide amplification of key messages across M1–M30 |

Dissemination

Z-Health will implement a targeted dissemination strategy to ensure that project findings, methods, tools and recommendations reach those actors most able to apply, adapt, support or scale them. Dissemination will focus in particular on scientific communities, policymakers and public authorities, public health actors, practitioners, education and youth-serving organisations, civil society and relevant intermediary networks at European, national and, where relevant, local level. Measures will include scientific publications and conference presentations; policy-oriented outputs such as briefs, summaries and stakeholder notes; practice-oriented resources and implementation-relevant materials; webinars, workshops and peer-learning exchanges; and dissemination through consortium and partner networks. Dissemination activities will be phased in line with project progress, beginning with the positioning of Z-Health and its approach, and increasingly focusing on emerging findings, implementation lessons, evaluation results and policy-relevant insights as these become available. Outputs and messages will be tailored to the needs, language and decision contexts of different audiences, with attention to accessibility, usability and health equity.

Exploitation

Z-Health will pursue exploitation pathways that support the uptake and practical use of its key results beyond the consortium. Exploitable results may include evidence and evaluation findings, intervention approaches and related materials, methodological tools, practice-oriented resources, implementation insights, and policy-relevant outputs arising from modelling, policy simulation and foresight work. Exploitation will focus primarily on non-commercial uptake through policy, practice, service, education and community settings, while also supporting transferability, adaptation and wider use by relevant actors across Europe. Potential pathways will be assessed during the project in relation to relevance, feasibility, ownership, transferability, scalability and added value. Particular attention will be paid to how exploitation can support equitable reach and benefit, including for older adolescents and young adults in vulnerable situations or at greater risk of exclusion. Exploitation planning will be closely linked to stakeholder engagement, dissemination and the final project event, which will help identify realistic opportunities for uptake, continuation and embedding of results.

Sustainability beyond the duration of Z-Health

From the outset, Z-Health will consider how its most valuable results, resources and partnerships can continue beyond the funded period. Sustainability will be pursued through several complementary routes: embedding relevant outputs in the work of consortium partners and their networks; supporting the continued use and adaptation of tools, materials and approaches in policy, practice and implementation settings; linking project outputs to ongoing European, national and local initiatives; and identifying follow-up opportunities for further research, implementation and scale-up. Particular importance will be given to sustaining those outputs with the greatest potential to inform policy and practice, strengthen prevention efforts, and contribute to fairer health outcomes for older adolescents and young adults. A final exploitation and sustainability framework will identify concrete options for continuation, ownership, stewardship and longer-term use of key project results.

Policy feedback

Z-Health will also generate feedback relevant to policy design, implementation, monitoring and review. Through its work on implementation, evaluation, modelling, policy simulation and foresight, the project will provide evidence and practical insight that can inform existing and emerging policy and programmatic measures relating to youth health, prevention, health equity and related service and community systems. Policy feedback will be channelled through tailored policy-oriented outputs, stakeholder dialogues, targeted briefings, and the project’s engagement with relevant European and national policy and professional networks. This will help position Z-Health not only as a research project, but also as a source of actionable intelligence for more effective and equitable policy and practice.

Intellectual property, ownership and access rights

Z-Health will develop an appropriate approach to intellectual property, ownership and access rights in line with Horizon Europe requirements and the future consortium agreement. Given the nature of the project, exploitation is expected to rely primarily on uptake, adaptation and use of knowledge, tools, methods and resources in public-interest, policy, service and community settings rather than on commercialisation. Where relevant, suitable protection and management measures, including copyright, licensing arrangements, access rights, data governance and recognition of background and foreground knowledge, will be applied to support appropriate use and longer-term exploitation of project results. Ownership and access conditions for key results will be clarified by the consortium in order to enable both collective and partner-specific uptake opportunities.

Taken together, these measures will help ensure that Z-Health is not only visible during its lifetime, but also that its results are disseminated effectively, used meaningfully, and positioned for longer-term uptake and impact in research, policy, practice and community contexts.

2.3 Summary (optional – Please remove this section if not used)

KEY ELEMENT OF THE IMPACT SECTION

| SPECIFIC NEEDS | EXPECTED RESULTS | D & E & C MEASURES |
| --- | --- | --- |
| What are the specific needs that triggered this project? Example 1 Most airports use process flow-oriented models based on static mathematical values limiting the optimal management of passenger flow and hampering the accurate use of the available resources to the actual demand of passengers. Example 2 Electronic components need to get smaller and lighter to match the expectations of the end-users. At the same time there is a problem of sourcing of raw materials that has an environmental impact. | What do you expect to generate by the end of the project? Example 1 Successful large-scale demonstrator: Trial with 3 airports of an advanced forecasting system for proactive airport passenger flow management. Algorithmic model: Novel algorithmic model for proactive airport passenger flow management. Example 2 Publication of a scientific discovery on transparent electronics. New product: More sustainable electronic circuits. Three PhD students trained. | What dissemination, exploitation and communication measures will you apply to the results? Example 1 Exploitation: Patenting the algorithmic model. Dissemination towards the scientific community and airports: Scientific publication with the results of the large-scale demonstration. Communication towards citizens: An event in a shopping mall to show how the outcomes of the action are relevant to our everyday lives. Example 2 Exploitation of the new product: Patenting the new product; Licencing to major electronic companies. Dissemination towards the scientific community and industry: Participating at conferences; Developing a platform of material compositions for industry; Participation at EC project portfolios to disseminate the results as part of a group and maximise the visibility vis-à-vis companies. |

| TARGET GROUPS | OUTCOMES | IMPACTS |
| --- | --- | --- |
| Who will use or further up-take the results of the project? Who will benefit from the results of the project? Example 1 9 European airports: Schiphol, Brussels airport, etc. The European Union aviation safety agency. Air passengers (indirect). Example 2 End-users: consumers of electronic devices. Major electronic companies: Samsung, Apple, etc. Scientific community (field of transparent electronics). | What change do you expect to see after successful dissemination and exploitation of project results to the target group(s)? Example 1 Up-take by airports: 9 European airports adopt the advanced forecasting system demonstrated during the project. Example 2 High use of the scientific discovery published (measured with the relative rate of citation index of project publications). A major electronic company (Samsung or Apple) exploits/uses the new product in their manufacturing. | What are the expected wider scientific, economic and societal effects of the project contributing to the expected impacts outlined in the respective destination in the work programme? Example 1 Scientific: New breakthrough scientific discovery on passenger forecast modelling. Economic: Increased airport efficiency Size: 15% increase of maximum passenger capacity in European airports, leading to a 28% reduction in infrastructure expansion costs. Example 2 Scientific: New breakthrough scientific discovery on transparent electronics. Economic/Technological: A new market for touch enabled electronic devices. Societal: Lower climate impact of electronics manufacturing (including through material sourcing and waste management). |

3. Quality and efficiency of the implementation

3.1	Work plan and resources

12 PAGES INCLUDING TABLES

OVERALL STRUCTURE OF THE WORK PLAN

Insert here text for your proposal

GANTT CHART OR SIMILAR

Insert here the figure

PERT CHART OR SIMILAR

DETAILED WORK DESCRIPTION

| WP | WP Title | Part. n. | Lead | PM | Start | End |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Project Coordination & Management |  |  |  |  |  |
| 2 | Ethics |  |  |  |  |  |
| 3 | NCD Evidence Framework & Disease Context |  |  |  |  |  |
| 4 | Multi-component intervention 1, Co-creation and planning: lower secondary school/early adolescence (age 12-15) |  |  |  |  |  |
| 5 | Multi-component intervention 1, Co-creation and planning: upper secondary school/late adolescence (age 16-18) |  |  |  |  |  |
| 6 | Intervention implementation in countries |  |  |  |  |  |
| 7 | Evaluation |  |  |  |  |  |
| 8 | Modelling, Policy simulation & Foresight |  |  |  |  |  |
| 9 | Communication, Stakeholder engagement, dissemination and exploitation |  |  |  |  |  |

Work package description

- For each task or element of the work package, describe all activities to be carried out and quantify them (e.g., number of protocols, tests, measurements, combinations, study subjects, conferences, publications, etc.).

- Resources assigned to work packages should be in line with their objectives and deliverables. You are advised to include a distinct work package on ‘project management’, and to give due visibility in the work plan to ‘data management’ ‘dissemination and exploitation’ and ‘communication activities’, either with distinct tasks or distinct work packages.

| Work package number | 1 |
| --- | --- |
| Work package title | Project Coordination & Management |
| Objectives. (1) to conduct project coordination; (2) to lead production of the consortium agreement and project implementation plan; (3) to facilitate WP connections and external cooperation with regular meetings; (4) to conduct central planning and management of sensitive topics (AI, privacy, security, ethics, gender, data, service design); (5) to conduct financial and regular reporting to EC. |  |
| Description of work T1.1 Scientific & Technical management (Lead: ICL; Participants: ALL PARTNERS) This task coordinates interactions between WPs and it is responsible for the supervision of the overall progress of the project, pursuing the conformance with deadlines and technical objectives. Specific documentation (presentations and procedures) will be prepared by the project coordinator and presented in a specific meeting to all the WP leaders within the kick-off meeting. WP leaders will be in charge of transferring this information to all the task leaders of their WP, having a 3-month cycle sprint meeting, helping the task leaders overcome impediments and establishing contingency plans for deviations, planning the review meetings at the end of each sprint and transfer results and information to other WP in the project progress meetings. Activities within this task, including detection of errors and deviations in the project’s life cycle and corrective actions or contingency plans, will be reported in the periodic reports. Enforce the quality assurance procedures, which is joint responsibility of all partners applied at all levels of the project’s activities. T1.2 Administrative and Operative management (Lead: ISINNOVA, Participants: ALL PARTNERS) Formal & legal relationship between Partners & the various constitutive components of the Consortium & the CE. It includes the maintenance and enactment of the provisions of the Consortium Agreement and the creation and maintenance of the various operational structures and communication tools. It will also monitor the implementation of the planned work, deadlines and milestones, follow-up of progress based on the DoA, financial & resource monitoring of the project, controlling schedule & consistency of deliverables. Planning (six-monthly Steering Committee and annual General Assembly) meetings to ensure information exchange and joint work execution. Remote and in-person meetings. Deal with the preparation of any modifications to the Description of Action (DoA) required by the results of annual reviews, partnership changes, or external factors. Periodic Reports. Ensuring that all contractual, society and gender equality issues related to the project research are properly considered and any relevant conventions are respected. T1.3 Quality and Risk management (Lead: ISINNOVA, Participants: WP LEADERS) This task will create a plan for the identification of risks and definition of procedures for their mitigation and resolution. This will be included in DX.X. This task will guarantee that the scientific and technical results of the project have been produced based on high quality standards. It will implement and maintain a quality assurance plan that will provide a single point of reference on the quality that will be governed during the project. Moreover, this task will deal with any potential risks and perform and evaluated within the whole project duration. The methodology to be followed for risk management consists of four steps: a) risk identification where areas of potential risk will be identified and classified, b) risk quantification where the probability of events will be determined and the consequences associated with their occurrence will be examined, c) risk response where methods will be produced to reduce or control the risk, and d) risk control and report where lessons learnt will be documented. T1.4 Ethical issues and data management (Lead: ICL, Participants: WP LEADERS) This task will establish processes for handling all likely legal or ethical issues according to section 5 (Ethics and Security). An Ethics & Privacy Officer (EPO), in charge of providing advice about how to to address any ethical issues arising in the project, will be appointed. Activities will be reported within the project’s Periodic Management Reports. It includes the following activities: a data management plan will be developed, maintained, and implemented, outlining which data will be generated and how they will be managed during research and piloting; metadata, standards and quality assurance measures; plans for sharing data; copyright and IPR of data; data storage and back-up measures; data management roles and responsibilities as well as and ensure comparability and consistency of the collected data across the groups of interest; monitoring project activities (especially activities related to tenure of user-generated content) strictly follow legal, ethical and security procedures dictated by National and EU regulations. This will include a consideration of the GDPR, as well as social and ethical issues like privacy, human rights, gender, and cultural implications; Keeping record of all potential ethical and security issues which arise as the groups of interest are running and prototypes are evaluated; Ensuring that Social Science Humanities (SSH) is embedded in the project as an enabler of Responsible Research Innovation (RRI). DELIVERABLES - Project Management Handbook – M3 (Definition of the meetings, representatives of each partner and WP leaders, internal communication strategy and risk and contingency plan) - Data and knowledge Management plan – M6 (Definition of the items that are subjected to intellectual property and the procedures to exchange information among thepartners. Updates will be informed during project reports) - Ethics report – one per period– M18 – M24 - M36 (Addressed the ethical requirements) - Intermediate Progress report M12 – M24 – M26 (Report of the scientific and technical activities carried out in the project) - Final report M42 MILESTONES - Kick off meeting organised M2 - Project management handbook submitted M3 - Data management plan submitted M6 |  |

| Work package number | 2 |
| --- | --- |
| Work package title | Ethics |

Objectives

Description of work T2.1 TITLE (lead partner – role of participants) Insert here text T2.n TITLE (lead partner – role of participants) Insert here text

| Work package number | 3 |
| --- | --- |
| Work package title | NCD Evidence Framework & Disease Context |

Objectives

Description of work T3.1 TITLE (lead partner – role of participants) Insert here text T3.n TITLE (lead partner – role of participants) Insert here text

| Work package number | 4 |
| --- | --- |
| Work package title | Multi-component intervention 1, Co-creation and planning: lower secondary school/early adolescence (age 12-15) |

Objectives

Description of work T4.1 TITLE (lead partner – role of participants) Insert here text T4.n TITLE (lead partner – role of participants) Insert here text

| Work package number | 5 |
| --- | --- |
| Work package title | Multi-component intervention 1, Co-creation and planning: upper secondary school/late adolescence (age 16-18) |

Objectives

Description of work T5.1 TITLE (lead partner – role of participants) Insert here text T5.n TITLE (lead partner – role of participants) Insert here text

| Work package number | 6 |
| --- | --- |
| Work package title | Intervention implementation in countries |
| Objectives The aim of WP6 is to ensure that proposed interventions are not only theoretically sound innovations but would be also effectively translated and implemented at the national and possibly regional and local levels by national institutes of public health in six (>5) participating countries. This work package addresses three key dimensions: 1. Common denominators of interventions: Identification of the shared mechanisms and principles across all interventions to enable harmonization and standardized approaches where feasible. 2. National implementation feasibility: Assess whether each intervention can be scaled up and institutionalized and integrated into the national context. This includes identifying necessary adaptations, relevant national stakeholders and right-holders to support, vulnerable groups and groups at risk (addressing inequalities), and assessing sustainability. Implementation science principles will guide the analysis to ensure that the interventions follow evidence-based, structured pathways from pilot to nationwide application. 3. Alignment of the proposed outcomes and recommendations with EU regulatory frameworks: Analyze how interventions relate to European legislation, such as the Digital Services Act (DSA), AVMSD, Healthier together, EU Beating Cancer plan and Safe Hearts Plan, Child Guarantee of EPSR and others. Final aim is to understand which principles can be harmonized and operationalized within the interventions, providing a clear framework for implementation. |  |
| Description of work T6.1 TITLE (lead partner – role of participants) Insert here text T6.n TITLE (lead partner – role of participants) Insert here text T6.1 Contextual analysis and implementation capacities addressing digital environment influences on youth NCD risk, in six EU countries (represented by the national public health institutes) Lead partner, together with partners from participating NIPHs will provide the baseline assessment of the key capacities in partners organizations, especially in the aspect of digitalization, important for the successful and long term implementation of the interventions: staff capacities, knowledge capacities, financial capacities, institutional and leadership capacities. Exploratory contextual analyses will be provided, to increase the understanding of the national contexts, priorities, and strategic/political environment at the national and EU level – to increase the understanding of the conditions for the implementation of the interventions and provide inputs for finetuning or adapting the implementation processes in participating countries. Structure – agency interplay, equity aspects (gender and geographical equity) and migration background would be specifically addressed. To improve the implementation potential, project relevant capacity building activities would be developed and provided to the implementation teams in six countries. In the last year of the project, follow-up assessment of the institutional capacities will be provided and lessons learnt for the implementation of the interventions will support the development of the final recommendations. T6.2 Stakeholder mapping (lead partner – role of participants) In stakeholder mapping process, relevant national and EU stakeholders and right-holders for the individual interventions would be identified, by their demography (public – private, profit-nonprofit, formal-nonformal, type, orientation, power, others). Basic stakeholder network analysis will be provided, to better understand the alliances and relationships among project stakeholders, including their power and direction of influence. Special interest will be paid to the possible conflicts of interest and influences in the individual interventions. Alignment with the relevant existing intersectoral groups or support to the establishment of the new intersectoral groups would be highly encouraged in the national context. Intersectoral groups could increase multidisciplinary competences of the national intervention teams and thus increase the opportunities for successful implementation of different types of intervention. Each of the partners will be establishing collaboration the up-mentioned collaboration and actions aligned with the national contexts. Meaningful engagement of youth is the key principle of the project and youth engagement would be elaborated specifically. T6.3 Core implementation science activities (lead partner – role of participants) Implementation science principles and frameworks will be applied to support the implementation of the interventions, to assess critical steps, target groups, and sustainability of each intervention. Understanding of the accountability cycle step three (holding to the account), linked to the effectiveness of the intervention, will be especially targeted by the implementation science approaches during the intervention, hopefully giving good insights into the nature of the intervention. Models such as Knowledge-to-Action Model (Graham s sod., 2006) or Quality Implementation Framework (Meyers s sod., 2012) would be explored for relevance for actions in the Z-HEALTH project. Interventions will be clustered using common denominators (existence of the strategic grounding (legislative) document to increase the legacy of the intervention; level of implementation - nat., reg-local; (gender) equity addressed; available capacities for implementation; transferability addressed; proportion of the population included in the intervention; addressed health determinants / NCDs / mental health; right-holders, vulnerable groups, migrants, youth engaged, rural /urban location; …and possible others, to be decided during the course of the project) and compared among themselves in that regard. Sustainability elements of the interventions will be explored in addition, to assure higher probability of long-term implementation of interventions and to increase the understanding what are the institutional characteristics influencing successfulness and effectiveness of the implementation of interventions. T6.4 Case studies (lead partner – role of participants) Participating countries would write the case studies, framed and structured, about the implemented interventions. Guiding questions for the case studies would be developed and common denominators of the interventions would be used, to enable intervention teams to write case studies in a harmonized manner. Case studies would be analyzed by the leading partner, in strong collaboration with the participating teams. Final report with lessons learnt would be provided in the first part of year four of the project. T6.5 Synthesis and recommendations (lead partner – role of participants) Based on the comprehensive analysis of and lessons learned from the provided case studies, actionable and sustainable recommendations for national and EU-level scaling-up of the proposed interventions will be provided for different health determinants and elaborated upstream determinants. Recommendations will be formulated embedded in the EU and national policy and legislative frameworks linked to health determinants, NCDs and mental health and digital environment, as a minimum. |  |
| Deliverables D6.n name – short description – Delivery date Milestones Milestone name – Delivery date Critical risks Any plausible event or issue that could have a high adverse impact on the ability of achieve the objectives. |  |

| Work package number | 7 |
| --- | --- |
| Work package title | Evaluation |

Objectives

Description of work T7.1 TITLE (lead partner – role of participants) Insert here text T7.n TITLE (lead partner – role of participants) Insert here text

| Work package number | 8 |
| --- | --- |
| Work package title | Sustainable implementation, Policy simulation & Foresight |
| Objectives - Identify emerging behavioural, social, and technological trends shaping youth health behaviours and NCD risk factors. - Explore plausible future scenarios to 2040 affecting the effectiveness, scalability and equity of behavioural interventions in different youth segments and contexts - Integrate foresight and modelling to assess the long-term robustness, adaptability and policy relevance of intervention strategies under alternative future conditions - Generate forward-looking policy recommendations, adaptation pathways and communication outputs to support sustainable implementation and uptake. |  |
| Description of work Task 8.1 – Horizon scanning, prioritisation of drivers and participatorysense-making (Lead: ISINNOVA) This task initiates the foresight cycle through a structured horizon scanning and sense-making process aimed at identifying critical drivers of change, emerging trends, weak signals, and potential disruptions shaping youth health behaviours,NCD risk factors and exposure pathways linked to NCD prevention. The task combines: (i) systematic desk research and rieview of scientific, grey and foresight literature; (ii) social media signal scanning across platforms and online spaces relevant to diverse youth segments, in order to to detect evolving behaviours, attitudes, narratives, motivations, barriers and inequalities; (iii) stakeholder-informed inputs, including semi-structured interviews with multidisciplinary experts, to refine and contextualise emerging insights; and (iv) collective and participatory sense-making exercises with a multidisciplinary panel (including youth representatives) to identify key trends, potential mismatches with intervention assumptions, and early warning signals of unintended consequences or exclusion. A Delphi-inspired survey process will then be used to assess the relevance and uncertainty of identified drivers and to prioritise key trends and critical uncertainties. The main outputs of this phased task will be a validated evidence base for scenario development (T8.3) and for assessing the future robustness and equity implications of Z-HEALTH interventions (T8.4). Task 8.2 Policy simulation and modelling of long-term impacts ( ICL – role of participants) This task will model the long-term health and policy implications of scaling Z-HEALTH interventions under alternative implementation and policy conditions. Building on intervention evidence generated by the project and informed by the outputs of Task 8.1, the modelling work will estimate the potential long-term effects of selected intervention strategies on youth health trajectories and NCD-related outcomes. The task will develop policy simulation scenarios to assess the likely impacts, cost-effectiveness, and distributional implications of intervention uptake across different socio-economic and national contexts. It will also identify the parameters and indicators most relevant for linking foresight outputs to modelling assumptions, ensuring that scenario narratives developed in WP8 can inform quantitative projections. The task will work in close interaction with the evaluation and intervention WPs to ensure methodological alignment and consistency of assumptions. This task will generate the modelling backbone for the integrated policy pathways developed later in WP8. Task 8.3 Scenario development and stress testing of interventions (Lead: ISINNOVA) Building on the prioritised trends and uncertainties identified in T8.1,, this task will develop a coherent scenario space and a set of 3–4 plausible future scenarios (to 2040) describing how youth health behaviours and key drivers of Non-Communicable Diseases (NCDs) may evolve.The scenarios will be co-developed through participatory foresight methods involving youth representatives, researchers, and stakeholders, ensuring diversity of perspectives and analytical relevance. The process will include a scenario consolidation workshop to collaboratively define key axes of uncertainty derived from the prioritised drivers and construct contrasting scenario logics capturing alternative evolutions of behavioural dynamics, social norms, and structural determinants affecting youth. Scenario narratives will then be elaborated and validated through structured consistency checks and expert validation to ensure analytical rigour, coherence, and plausability. Particular attention will be paid to how emerging trends in digital platforms, social norms, commercial exposure patterns, institutional trust, and regulatory conditions may reshape behavioural dynamics and intervention contexts across socio-economic and cultural settings. The scenarios will subsequently be used as a framework to stress test behavioural interventions targeting NCD prevention and associated policy approaches. This will assess: - robustness and fragility of intervention mechanisms under different future conditions - scalability and transferability across youth segments and countries - potential equity implications, including risks of exclusion or widening inequalities - needs for policy adjustment, complementary measures, or safeguarding mechanisms This task will provide the strategic bridge between qualitative foresight and quantitative modelling, and will support the development of future-proof intervention and policy pathways in T8.4. Task 8.4 Evaluation of integrated pathways, policyrecommendations and foresight uptake (ICL/ISINNOVA) This task will synthesise the findings from modelling and foresight into actionable policy pathways and recommendations to support the sustainable implementation of Z-HEALTH interventions. It will identify how interventions may need to be adapted, combined, or sequenced under different future conditions, and which regulatory, educational, communicative, and infrastructural levers are needed to support their implementation and scale-up. The task will translate the integrated outputs of Tasks 8.2 and 8.3 into policy-relevant recommendations for EU, national, and local actors, with attention to intervention effectiveness, equity, and long-term resilience. [EXPAND ON RECOMMENDATION ACTIVITIES AND APPROACH] It will also generate a communication-oriented output stream, including open-access web-based foresight storylines and visual narratives, developed in coordination with WP9, to support dissemination, strengthen stakeholder engagement, and increase the long-term impact of foresight visions. The storylines will translate trends, uncertainties, scenarios, and policy insights into accessible and visually engaging narratives for policymakers, practitioners, educators, youth organisations and the wider public. Structured around two main sections, Challenges and Visions, the platform will combine concise texts, infographics, and interactive elements to illustrate how youth health behaviours and intervention conditions may evolve towards 2040. Youth participants will contribute to the co-creation and validation of the storylines, ensuring relevance, credibility, and communication value. |  |
| Deliverables D8.X – Horizon scanning and participatory sense-making report D8.X - Policy simulation framework and modelling report D8.X – Foresight scenarios report on future drivers of youth health behaviours D8.X – Policy pathways and recommendations report (integrating foresight and modelling) D8.X - Web-based foresight storylines Milestones MS8.X – Completion of horizon scanning and validation of key trends/uncertainties MS8.X Set of future scenarios (2035–2040) developed and validated through stakeholder and youth workshops, ensuring relevance, diversity of perspectives, and policy applicability. Critical risks Limited or biased participation of youth and stakeholders; Medium; High; Targeted stakeholder recruitment; collaboration with youth organisations; inclusive and hybrid engagement formats; attention to diversity across age, gender, socio-economic background, and cultural context.. Weak integration of foresight outputs with modelling and policy tasks; Medium; High; Early alignment with modelling team; joint workshops; iterative feedback loops; co-development of policy-relevant indicators. |

| Work package number | 9 |
| --- | --- |
| Work package title | Communication, Stakeholder engagement, dissemination and exploitation |
| Objectives. (1) to establish and implement the project’s plan for dissemination and exploitation including communication activities; (2) to ensure effective and targeted communication and dissemination of Z-Health activities, findings and outputs to relevant stakeholder groups; (3) to engage stakeholders and multiplier networks throughout the project so as to strengthen relevance, visibility, ownership and uptake of results; (4) translate evaluation findings, implementation experience, and modelling and foresight outputs into accessible and policy- and practice-relevant dissemination products; (5) to prepare pathways for exploitation, transferability and sustainability of key project results beyond the funded period. |  |
| Description of work T9.1 Dissemination, exploitation and communication plan (DEC Plan) (Lead: EHNet, Participants: WP1 (ICL), WP7, WP8 LEADERS, WP6 implementation partners, digital/web support) This task will develop the project’s plan for dissemination and exploitation including communication activities within the first 6 months of the project, and update it as needed during implementation. It will define target audiences, core messages, communication channels, dissemination formats, stakeholder groups, exploitation routes, responsibilities across the consortium, and indicators for monitoring outreach and uptake. The task will ensure alignment with the overall project governance under WP1 and close coherence with the evidence, implementation, evaluation and modelling work developed across the project. T9.2 Communication and project visibility (Lead: EHNet, Participants: WP1 (ICL) and WP3 LEADERS; WP6 implementation partners; ALL PARTNERS) This task will implement the project’s communication activities and support a clear, coherent and accessible external profile for Z-Health. It will cover core messaging, communication materials, website and digital channels, promotion of key milestones, and support to partners in outreach and visibility activities. Communication will be tailored to different audiences and calibrated to the project’s equity objectives, including attention to vulnerable, underserved and less-heard groups. Where relevant, communication approaches and messages will be informed through co-design and participatory mechanisms involving people with lived experience and relevant advisory bodies, including youth and community networks. In line with the project’s social and human sciences perspective, the task will promote communication that is inclusive, context-sensitive and responsive to the realities of different population groups. T9.3 Stakeholder engagement and targeted dissemination (Lead: EHNet, Participants: WP6 implementation partners; WP1 (ICL), WP3, WP4, WP5, WP7 and WP8 LEADERS; stakeholder-facing partners) This task will engage relevant stakeholders and multiplier networks at European, national and local levels, and support the targeted dissemination of project findings and outputs to policy, practice, research and community audiences. It will include stakeholder mapping, tailored outreach, participatory and deliberative engagement approaches, and dissemination through partner networks. Particular attention will be paid to vulnerable, underserved and less-heard groups, including through the involvement of people with lived experience and, where relevant, youth and community advisory structures. In line with the project’s equity objectives and social and human sciences perspective, the task will help ensure that Z-Health outputs are communicated in ways that are inclusive, relevant and responsive to different contexts, and that strengthen ownership and uptake. The task will also include preparation and delivery of a final project event to present and discuss key findings, implementation lessons and policy- and practice-relevant messages with relevant stakeholder audiences. T9.4 Exploitation, uptake and sustainability of project results (Lead: EHNet, Partners: WP1 (ICL), WP4, WP5, WP7 and WP8 LEADERS; WP6 implementation partners; partners owning key tools or interventions) This task will prepare the exploitation, uptake and sustainability of key Z-Health results beyond the project period. It will identify exploitable outputs, assess their transferability and scale-up potential, and develop pathways for their use in policy, practice, service and community settings. Building particularly on evaluation findings, implementation experience, and modelling and foresight outputs, the task will support exploitation approaches that are credible, context-sensitive and relevant to end users. In line with the project’s equity objectives, attention will be paid to fairer access, reach and benefit, including for vulnerable and less-heard groups. The task will culminate in a final exploitation and sustainability framework. In close link with T9.3, this task will contribute to the preparation of the final project event as a platform to showcase key results and to stimulate dialogue on their uptake, transferability, scale-up potential and sustainability beyond the project period. |  |

List of Deliverables

| Number | Deliverable name | Short description | WP n. | Lead participant | Type | Dissemination level | Delivery date |
| --- | --- | --- | --- | --- | --- | --- | --- |
| D9.1 | Dissemination, exploitation and communication plan (DEC Plan) | Strategic plan setting out the project’s approach to communication, dissemination, stakeholder engagement and exploitation, including target audiences, key messages, channels, stakeholder engagement structures, advisory mechanisms, roles, timeline and indicators for monitoring outreach and uptake. | WP9 | EHNet | R/DEC | SEN | M6 |
| D9.2 | Inclusive communication and stakeholder engagement toolkit | Practical communication and stakeholder engagement package including the project narrative and messaging framework, visual identity elements, communication templates, website and digital content approach, and guidance for accessible, equity-sensitive and audience-tailored dissemination and engagement across the consortium. | WP9 | EHNet | OTHER/DEC | SEN | M9/M12 |
| D9.3 | Stakeholder engagement and dissemination report | Interim/final report on stakeholder engagement and dissemination activities undertaken, including stakeholder mapping, participatory and deliberative engagement approaches, use of advisory mechanisms, dissemination products and channels used, and plans for major dissemination moments including the final project event. | WP9 | EHNet, WP LEADERS, ALL PARTNERS | R | SEN | M18/M20 |
| D9.4 | Final exploitation and sustainability framework | Final framework for exploitation, uptake and sustainability of key Z-Health results, identifying exploitable outputs, transferability and scale-up potential, pathways for institutional uptake, and key messages and follow-up opportunities emerging from the final project event. | WP9 | EHNet, WP LEADERS, ALL PARTNERS | R | SEN | M27/M30 |

KEY Deliverable numbers in order of delivery dates. Please use the numbering convention <WP number>.<number of deliverable within that WP>. For example, deliverable 4.2 would be the second deliverable from work package 4. Type: Use one of the following codes: R: Document, report (excluding the periodic and final reports) DEM: Demonstrator, pilot, prototype, plan designs DEC: Websites, patents filing, press & media actions, videos, etc. DATA: Data sets, microdata, etc. DMP: Data management plan ETHICS: Deliverables related to ethics issues. SECURITY: Deliverables related to security issues OTHER: Software, technical diagram, algorithms, models, etc. Dissemination level: Use one of the following codes: PU – Public, fully open, e.g. web (Deliverables flagged as public will be automatically published in CORDIS project’s page) SEN – Sensitive, limited under the conditions of the Grant Agreement Classified R-UE/EU-R – EU RESTRICTED under the Commission Decision No2015/444 Classified C-UE/EU-C – EU CONFIDENTIAL under the Commission Decision No2015/444 Classified S-UE/EU-S – EU SECRET under the Commission Decision No2015/444 Delivery date Measured in months from the project start date (month 1)

List of milestones

| Milestone number | Milestone name | Related WPs | Due date (in month) | Means of verification |
| --- | --- | --- | --- | --- |
| MS9.1 | Dissemination, exploitation and communication plan approved | WP9, WP1 | M6 | Approval of D9.1 by the consortium/governing bodies; plan submitted |
| MS9.2 | Communication and stakeholder engagement and advisory mechanisms operational | WP9, WP6, WP7 | M9/12 | Core communication materials and channels established; stakeholder mapping completed; relevant advisory and participatory engagement mechanisms initiated. |
| MS9.3 | Targeted dissemination and engagement activities underway | WP9, WP7, WP8 | M18/20 | Evidence of dissemination outputs and stakeholder engagement activities implemented for key target groups; interim progress documented |
| MS9.4 | Exploitation and sustainability pathways consolidated and presented | WP9, WP7, WP8, WP1 | M27/30 | Key exploitable outputs, uptake routes and sustainability options identified; final project event held with relevant stakeholder participation. |

KEY Due date Measured in months from the project start date (month 1) Means of verification Show how you will confirm that the milestone has been attained. Refer to indicators if appropriate. For example: a laboratory prototype that is ‘up and running’; software released and validated by a user group; field survey complete and data quality validated.

Critical risks for implementation

| Risks related to the horizontal aspects: Management and dissemination |  |  |
| --- | --- | --- |
| Description of risk | WP | Proposed risk-mitigation measures |
| 1. Withdrawal of partner(s) A partner could decide to discontinue the collaboration and leave the consortium. Likelihood: Low. Severity: High |  | The PC prepares a proposal for replacement / swap of activities, including partial or total reallocation to existing partners. A contract amendment is agreed with the consortium and proposed to the EC |
| 2. Communication Misunderstandings, resulting from poor communication, can cause delay in the workplan and/or reduce the clarity of project functioning. Likelihood: Low. Severity: High |  | The PC reviews the communication procedures and channels, and design the necessary adjustments (additional meetings, revised formats, more detailed minutes, etc.). WP leaders will organise regular on- line meetings to ensure to a good coordination. |
| 3. Coordination problems within WP Roles and duties within a WP are not clearly assigned and causes delay to the WP activities Likelihood: Low. Severity: Medium |  | PC contacts WP leader to identify a solution, including (i) reallocation of responsibilities and resources, (ii) rescheduling of milestones and deliverables, (iii) identification of alternative courses of action. |
| 4. Delayed or unsatisfactory deliverable A deliverable not produced by the due date or with a satisfactory quality could delay i) the linked activities and/or ii) approval of periodic activity reports. Likelihood: Low. Severity: Medium |  | In case of prolonged delay or constant low quality of the deliverable, the PC will assign the task to another team/researcher, and modify the allocation of the EC contribution accordingly, in line with the provisions that will be set out in the Consortium Agreement |
| Risks related to the scientific aspects |  |  |
| Description of risk (indicate level of (i) likelihood, and (ii) severity: Low/Medium/High) | WP | Proposed risk-mitigation measures |
| 5. Intervention implementation |  |  |
| 6. Collection of the data in the site |  |  |
| 7. Stakeholder involvement |  |  |
| 8. Policymakers The connection with policymakers is less effective than planned. Likelihood: Low. Severity: High |  | Dissemination activities are carefully targeted to the relevant audiences and dissemination events are arranged well in advance. XXX will stay in regular contact with relevant policymakers to keep them apprised of the project’s progress. |

Definition critical risk: A critical risk is a plausible event or issue that could have a high adverse impact on the ability of the project to achieve its objectives. Level of likelihood to occur: Low/medium/high: The likelihood is the estimated probability that the risk will materialise even after taking account of the mitigating measures put in place. Level of severity: Low/medium/high: The relative seriousness of the risk and the significance of its effect.

Summary of staff effort

Please indicate the number of person/months over the whole duration of the planned work, for each work package, for each participant. Identify the work-package leader for each WP by showing the relevant person-month figure in bold.

| Participant n./name | WP1 | WP2 | WP3 | WP4 | WP5 | WPn | Total PMs |
| --- | --- | --- | --- | --- | --- | --- | --- |
| TOTAL |  |  |  |  |  |  |  |

‘Subcontracting costs’ items

For each participant describe and justify the tasks to be subcontracted (please note that core tasks of the project should not be sub-contracted).

| Participant Number/Short Name |  |  |
| --- | --- | --- |
|  | Cost (€) | Description of tasks and justification |
| Subcontracting |  |  |

‘Purchase costs’ items (travel and subsistence, equipment and other goods, works and services)

| Participant Number/Short Name |  |  |
| --- | --- | --- |
|  | Cost (€) | Justification |
| Travel and subsistence |  |  |
| Equipment |  |  |
| Other goods, works and services |  |  |
| Total |  |  |

3.2	Capacity of participants and consortium as a whole

3 PAGES

The individual participants of the consortium are described in a separate section under Part A. There is no need to repeat that information here.

- Describe the consortium. How does it match the projet’s objectives, and bring together the necessary disciplinary and inter-disciplinary knowledge? Show how this includes expertise in social sciences and humanities, open science practices, and gender aspects of R&I, as appropriate. Include in the description affiliated entities and associated partners, if any.

- Show how the partners will have access to critical infrastructure needed to carry out the project activities.

- Describe how the members complement one another (and cover the value chain, where appropriate)

- In what way does each of them contribute to the project? Show that each has a valid role, and adequate resources in the project to fulfil that role.

- If applicable, describe the industrial/commercial involvement in the project to ensure exploitation of the results and explain why this is consistent with and will help to achieve the specific measures which are proposed for exploitation of the results of the project (see section 2.2).

- Other countries and international organisations: If one or more of the participants requesting EU funding is based in a country or is an international organisation that is not automatically eligible for such funding (entities from Member States of the EU, from Associated Countries and from one of the countries in the exhaustive list included in the Work Programme General Annexes B  are automatically eligible for EU funding), explain why the participation of the entity in question is essential to successfully carry out the project.

Insert here text for your proposal

ANNEXES TO PROPOSAL PART B

Some calls may ask to upload annexes to proposal part B. The annexes must be uploaded as separate documents in the submission system. The most common annexes to be uploaded in Horizon Europe are (standard templates are published in the Funding & Tenders portal):

- CLINICAL TRIALS: Annex with information on clinical trials

- FINANCIAL SUPPORT TO THIRD PARTIES: Annex with information on financial support to third parties.

- CALLS FLAGGED AS SECURITY SENSITIVE: Annex with information on security aspects.

- ETHICS: ethics self-assessment should be included in proposal part A. However, in calls where several serious ethics issues are expected, the character limited in this section of proposal part A may not be sufficient for participants to give all necessary information. In those cases, participants may include additional information in an annex to proposal part B.

For further guidance on communicating EU research and innovation for project participants, please refer to the Online Manual on the Funding & Tenders Portal

https://cdn.who.int/media/docs/default-source/reproductive-health/contraception-family-planning/stakeholder-mapping-tool.pdf;